## Dashboard
EXECUTION #116 - Digital Humans Test
Agent | Deliverable | Count/Size | Status
Sophie (PM) | Business Requirements | 20 BRs | ✅
Olivia (BA) | Use Cases | 78 UCs | ✅
Marcus (Architect) | As-Is Analysis | 6.8 KB | ✅
Marcus (Architect) | Gap Analysis | 25 KB | ✅
Marcus (Architect) | Solution Design | 19 KB | ✅
Marcus (Architect) | WBS | 84 KB | ✅
Elena (QA) | QA Specifications | 20.7 KB | ✅
Jordan (DevOps) | DevOps Specifications | 40 KB | ✅
Aisha (Data) | Data Specifications | 18 KB | ✅
Lucas (Trainer) | Training Specifications | 16.8 KB | ✅

## Sophie - BRs (20)
BR ID | Category | Requirement | Priority | Status
BR-001 | DATA_MODEL | The system must store customer feedback records with rating, comments, date, and association to a customer account. | SHOULD | VALIDATED
BR-002 | DATA_MODEL | Customer ratings must be captured using a standardized 1 to 5 star scale for consistency in measurement and reporting. | SHOULD | VALIDATED
BR-003 | DATA_MODEL | The system must allow customers to provide free-text comments along with their rating to capture qualitative feedback. | SHOULD | VALIDATED
BR-004 | DATA_MODEL | Each feedback record must capture the date when the feedback was submitted for tracking and reporting purposes. | SHOULD | VALIDATED
BR-005 | DATA_MODEL | Each feedback record must be associated with a specific customer account to enable account-level analysis and reporting. | SHOULD | VALIDATED
BR-006 | DATA_MODEL | Each customer account must have a field to store the calculated average rating from all associated feedback records. | SHOULD | VALIDATED
BR-007 | AUTOMATION | When a new feedback is submitted, the system must automatically recalculate the average rating for the associated account. | SHOULD | VALIDATED
BR-008 | AUTOMATION | When an existing feedback rating is modified, the system must automatically recalculate the average rating for the associated account. | SHOULD | VALIDATED
BR-009 | AUTOMATION | When a feedback record is deleted, the system must automatically recalculate the average rating for the associated account. | SHOULD | VALIDATED
BR-010 | UI_UX | Users must have access to a form interface on the account page to submit new customer feedback without navigating away. | SHOULD | VALIDATED
BR-011 | UI_UX | The feedback submission form must include a rating selector allowing users to choose a rating from 1 to 5 stars. | SHOULD | VALIDATED
BR-012 | UI_UX | The feedback submission form must include a text area for users to enter customer comments. | SHOULD | VALIDATED
BR-013 | UI_UX | When submitting feedback from an account page, the system must automatically link the feedback to that account. | SHOULD | VALIDATED
BR-014 | UI_UX | The system must confirm to the user when a feedback record has been successfully submitted. | SHOULD | VALIDATED
BR-015 | UI_UX | The feedback form must validate that required fields are completed before allowing submission. | SHOULD | VALIDATED
BR-016 | DATA_MODEL | The system must support migration of 50 historical feedback records from an external source into the new feedback structure. | SHOULD | VALIDATED
BR-017 | DATA_MODEL | A standardized CSV template must be provided to facilitate the import of historical feedback data with correct field mapping. | SHOULD | VALIDATED
BR-018 | DATA_MODEL | The migration process must validate that imported feedback data meets all business rules and data quality standards. | SHOULD | VALIDATED
BR-019 | AUTOMATION | After historical feedback data is migrated, all affected account average ratings must be recalculated to reflect the imported data. | SHOULD | VALIDATED
BR-020 | UI_UX | Users should be able to view all feedback records associated with an account from the account page. | SHOULD | VALIDATED

## Olivia - UCs (78)
UC ID | Parent BR | Title | Actor | Trigger | Main Flow | Alt Flows | Acceptance Criteria | SF Objects | SF Fields
UC-001-01 | BR-001 | Create Customer Feedback Record | Business User | User clicks New on Customer Feedback related list | 1. User clicks New on Customer_Feedback__c related list from Account 2. User enters Rating__c (1-5), Comments__c, and Feedback_Date__c 3. System auto-populates Account__c lookup with parent Account 4. User clicks Save 5. System validates required fields are populated 6. System creates Customer_Feedback__c record linked to Account | 5a. If Rating__c is blank: System displays error 'Rating is required' 5b. If Feedback_Date__c is future date: System displays error 'Feedback date cannot be in future' | GIVEN user is on Account record WHEN user creates feedback with valid data THEN Customer_Feedback__c record is created with Account__c populated GIVEN user submits feedback WHEN Rating__c is blank THEN error message displays and record is not saved GIVEN user enters future date WHEN user clicks Save THEN error message displays for Feedback_Date__c GIVEN feedback is saved WHEN user views Account THEN new feedback appears in related list | Account, Customer_Feedback__c | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Feedback_Date__c, Customer_Feedback__c.Account__c
UC-001-02 | BR-001 | Edit Existing Customer Feedback | Business User | User clicks Edit on Customer_Feedback__c record | 1. User opens Customer_Feedback__c record and clicks Edit 2. User modifies Rating__c or Comments__c fields 3. User clicks Save 4. System validates modified data 5. System updates Customer_Feedback__c record with timestamp | 4a. If Rating__c is outside 1-5 range: System displays error 'Rating must be between 1 and 5' 4b. If Account__c lookup is removed: System displays error 'Account association is required' | GIVEN existing feedback record WHEN user updates Rating__c or Comments__c THEN changes are saved successfully GIVEN user edits feedback WHEN Rating__c is invalid THEN error message displays and changes are not saved GIVEN user edits feedback WHEN Account__c is removed THEN error prevents saving GIVEN feedback is updated WHEN save is successful THEN LastModifiedDate is updated | Customer_Feedback__c, Account | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Account__c, Customer_Feedback__c.LastModifiedDate
UC-001-03 | BR-001 | View Customer Feedback on Account | Business User | User opens Account record | 1. User navigates to Account record 2. User scrolls to Customer Feedback related list 3. System displays all Customer_Feedback__c records linked to Account 4. User views Rating__c, Comments__c, and Feedback_Date__c in list view | 3a. If no feedback exists: System displays 'No records to display' message | GIVEN Account has feedback records WHEN user views Account THEN all related Customer_Feedback__c records display in related list GIVEN Account has no feedback WHEN user views Account THEN related list shows no records message GIVEN multiple feedback records exist WHEN user views list THEN records are sorted by Feedback_Date__c descending | Account, Customer_Feedback__c | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Feedback_Date__c, Customer_Feedback__c.Account__c
UC-001-04 | BR-001 | Delete Customer Feedback Record | Business User | User clicks Delete on Customer_Feedback__c record | 1. User opens Customer_Feedback__c record 2. User clicks Delete button 3. System displays confirmation dialog 4. User confirms deletion 5. System moves record to Recycle Bin 6. System removes record from Account related list | 4a. If user cancels: System returns to record detail page without deletion | GIVEN user has delete permission WHEN user confirms deletion THEN Customer_Feedback__c record moves to Recycle Bin GIVEN user deletes feedback WHEN deletion completes THEN record no longer appears on Account related list GIVEN user cancels deletion WHEN cancel is clicked THEN record remains unchanged | Customer_Feedback__c, Account | Customer_Feedback__c.IsDeleted, Customer_Feedback__c.Account__c
UC-002-01 | BR-002 | Capture Customer Rating on Account Record | Sales Rep | Sales Rep completes customer interaction and needs to record satisfaction rating | 1. Sales Rep opens Account record 2. Sales Rep clicks Edit on Account detail page 3. Sales Rep selects rating value from Customer_Rating__c picklist (1-5 stars) 4. Sales Rep clicks Save 5. System validates rating is between 1-5 6. System saves Account record with Customer_Rating__c populated | 3a. If Sales Rep leaves Customer_Rating__c blank: System allows save (rating is optional) 5a. If invalid value entered: System displays error 'Rating must be 1-5 stars' | GIVEN Sales Rep is on Account edit page WHEN they select a rating from 1-5 THEN Customer_Rating__c field saves selected value GIVEN Sales Rep selects rating value WHEN they click Save THEN only values 1, 2, 3, 4, or 5 are accepted GIVEN Account record exists WHEN Customer_Rating__c is populated THEN rating displays as star icons on Account detail page GIVEN multiple users access Account WHEN viewing Customer_Rating__c THEN all users see consistent 1-5 scale | Account | Account.Customer_Rating__c
UC-002-02 | BR-002 | Generate Customer Rating Report by Segment | Business Analyst | Business Analyst needs monthly customer satisfaction metrics | 1. Business Analyst navigates to Reports tab 2. Business Analyst creates new Account report 3. Business Analyst adds Customer_Rating__c field to report columns 4. Business Analyst groups report by Account.Type or Account.Industry 5. Business Analyst adds average formula for Customer_Rating__c 6. System calculates average rating per segment and displays results | 3a. If Customer_Rating__c is null for some records: System excludes null values from average calculation 6a. If no ratings exist for segment: System displays 0 or N/A | GIVEN Account records have Customer_Rating__c populated WHEN Business Analyst runs report THEN average rating calculates correctly (sum/count) GIVEN report includes Customer_Rating__c WHEN grouped by segment THEN each segment shows separate average rating GIVEN Accounts with null ratings exist WHEN calculating average THEN null values are excluded from calculation GIVEN report is saved WHEN other users access it THEN rating scale displays consistently as 1-5 | Account | Account.Customer_Rating__c, Account.Type, Account.Industry
UC-002-03 | BR-002 | Validate Rating Scale on Case Feedback | Support Agent | Support Agent closes Case and requests customer feedback rating | 1. Support Agent changes Case.Status to 'Closed' 2. Support Agent navigates to Case Feedback section 3. Support Agent enters Case_Feedback_Rating__c value (1-5 stars) 4. System validates rating is numeric and within 1-5 range 5. System saves Case record with Case_Feedback_Rating__c 6. System updates related Account.Customer_Rating__c with latest feedback average | 4a. If rating is outside 1-5 range: System displays error 'Please enter rating between 1 and 5 stars' 6a. If multiple Case ratings exist for Account: System calculates rolling average of last 10 Case ratings | GIVEN Support Agent enters Case feedback WHEN rating is 1-5 THEN Case_Feedback_Rating__c saves successfully GIVEN Support Agent enters invalid rating WHEN value is <1 or >5 THEN System prevents save and shows error message GIVEN Case is closed with rating WHEN Case_Feedback_Rating__c is saved THEN related Account.Customer_Rating__c updates automatically GIVEN Account has multiple Case ratings WHEN new rating is added THEN Account rating reflects average of recent feedback | Case, Account | Case.Status, Case.Case_Feedback_Rating__c, Account.Customer_Rating__c
UC-002-04 | BR-002 | Display Rating History on Account Timeline | Account Manager | Account Manager reviews customer satisfaction trends over time | 1. Account Manager opens Account record 2. Account Manager scrolls to Activity Timeline or Related List 3. System displays Customer_Rating_History__c records chronologically 4. Account Manager views Rating_Value__c (1-5), Rating_Date__c, and Rating_Source__c for each entry 5. Account Manager identifies rating trends (improving/declining) | 3a. If no rating history exists: System displays 'No ratings recorded' message 5a. If Account Manager needs detailed analysis: Account Manager exports rating history to Excel | GIVEN Account has rating history WHEN Account Manager views timeline THEN all Customer_Rating_History__c records display with 1-5 star values GIVEN multiple ratings exist WHEN displayed on timeline THEN records sort by Rating_Date__c descending (newest first) GIVEN rating history record exists WHEN viewed THEN Rating_Value__c shows only values 1, 2, 3, 4, or 5 GIVEN Account Manager reviews trends WHEN comparing ratings THEN consistent 1-5 scale enables accurate comparison | Account, Customer_Rating_History__c | Customer_Rating_History__c.Rating_Value__c, Customer_Rating_History__c.Rating_Date__c, Customer_Rating_History__c.Rating_Source__c, Customer_Rating_History__c.Account__c
UC-003-01 | BR-003 | Customer Submits Rating with Text Comment | Customer | Customer completes rating selection and enters comment text | 1. Customer selects rating value (1-5 stars) 2. Customer enters free-text comment in Comment__c field 3. Customer clicks Submit button 4. System validates comment length does not exceed 32,000 characters 5. System creates Customer_Feedback__c record with Rating__c and Comment__c populated 6. System displays confirmation message to customer | 2a. If customer leaves comment blank: System allows submission with null Comment__c value 4a. If comment exceeds character limit: System displays error 'Comment must be 32,000 characters or less' | GIVEN customer has selected a rating WHEN customer enters comment and clicks Submit THEN Customer_Feedback__c record is created with both Rating__c and Comment__c populated GIVEN customer has selected a rating WHEN customer leaves comment blank and clicks Submit THEN Customer_Feedback__c record is created with Rating__c populated and Comment__c null GIVEN customer enters 32,001 characters in comment WHEN customer clicks Submit THEN system displays character limit error and prevents submission GIVEN customer submits valid rating and comment WHEN submission completes THEN system displays 'Thank you for your feedback' confirmation | Customer_Feedback__c | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comment__c, Customer_Feedback__c.Customer__c, Customer_Feedback__c.Submission_Date__c
UC-003-02 | BR-003 | Customer Edits Existing Feedback Comment | Customer | Customer navigates to previously submitted feedback record | 1. Customer opens existing Customer_Feedback__c record 2. Customer clicks Edit button on Comment__c field 3. Customer modifies comment text 4. Customer clicks Save button 5. System updates Comment__c field value 6. System updates Last_Modified_Date__c timestamp | 1a. If feedback record is older than 30 days: System displays 'Editing not allowed for submissions older than 30 days' and disables Edit button 3a. If customer clears all comment text: System allows saving with null Comment__c value | GIVEN customer has feedback record less than 30 days old WHEN customer edits and saves comment THEN Comment__c is updated with new text and Last_Modified_Date__c is updated GIVEN customer has feedback record older than 30 days WHEN customer views record THEN Edit button is disabled and warning message is displayed GIVEN customer edits comment to blank WHEN customer saves THEN Comment__c is set to null and Rating__c remains unchanged | Customer_Feedback__c | Customer_Feedback__c.Comment__c, Customer_Feedback__c.Last_Modified_Date__c, Customer_Feedback__c.Submission_Date__c
UC-003-03 | BR-003 | Support Agent Reviews Customer Feedback Comments | Support Agent | Support agent accesses customer feedback dashboard | 1. Support agent navigates to Customer Feedback list view 2. Support agent filters records by date range and rating value 3. System displays filtered Customer_Feedback__c records with Comment__c visible 4. Support agent clicks on record to view full comment details 5. Support agent marks feedback as Reviewed__c = true 6. System timestamps Review_Date__c field | 3a. If Comment__c is null: System displays 'No comment provided' in list view 5a. If support agent adds internal note: System populates Internal_Notes__c field without modifying Comment__c | GIVEN support agent applies filters WHEN system displays results THEN all records show Rating__c and Comment__c values in list view GIVEN support agent marks feedback as reviewed WHEN save occurs THEN Reviewed__c = true and Review_Date__c = current timestamp GIVEN feedback has null Comment__c WHEN displayed in list view THEN 'No comment provided' text appears GIVEN support agent adds internal note WHEN saved THEN Internal_Notes__c is populated and Comment__c remains unchanged | Customer_Feedback__c | Customer_Feedback__c.Comment__c, Customer_Feedback__c.Rating__c, Customer_Feedback__c.Reviewed__c, Customer_Feedback__c.Review_Date__c, Customer_Feedback__c.Internal_Notes__c
UC-003-04 | BR-003 | System Analyzes Comment Sentiment for Reporting | System | Customer_Feedback__c record is created or Comment__c is updated | 1. System detects new or updated Comment__c value 2. System invokes Einstein Sentiment Analysis API with comment text 3. System receives sentiment score (Positive/Neutral/Negative) 4. System populates Sentiment__c field with analysis result 5. System updates Sentiment_Confidence__c with confidence percentage | 1a. If Comment__c is null or empty: System sets Sentiment__c = 'Not Applicable' and skips API call 2a. If API call fails: System logs error and sets Sentiment__c = 'Analysis Failed' | GIVEN Comment__c contains text WHEN record is saved THEN Sentiment__c is populated with Positive, Neutral, or Negative value GIVEN Comment__c is null WHEN record is saved THEN Sentiment__c = 'Not Applicable' and no API call is made GIVEN sentiment analysis completes WHEN result is received THEN Sentiment_Confidence__c shows percentage value between 0-100 | Customer_Feedback__c | Customer_Feedback__c.Comment__c, Customer_Feedback__c.Sentiment__c, Customer_Feedback__c.Sentiment_Confidence__c
UC-004-01 | BR-004 | Auto-capture submission date on feedback creation | Business User | User saves a new feedback record | 1. User navigates to Feedback object and clicks New 2. User enters required feedback details 3. User clicks Save 4. System auto-populates Feedback__c.Submission_Date__c with current date 5. System saves feedback record 6. System displays success message with submission date | 4a. If Submission_Date__c already has value: System retains original date | GIVEN user creates new feedback WHEN user clicks Save THEN Submission_Date__c equals today's date GIVEN feedback record exists WHEN user edits record THEN Submission_Date__c remains unchanged GIVEN Submission_Date__c is populated WHEN user views record THEN date displays in user's locale format | Feedback__c | Feedback__c.Submission_Date__c
UC-004-02 | BR-004 | Prevent manual modification of submission date | Business User | User attempts to edit Submission_Date__c field | 1. User opens existing feedback record in edit mode 2. System displays Submission_Date__c as read-only field 3. User modifies other feedback fields 4. User clicks Save 5. System saves changes without altering Submission_Date__c | 2a. If System Admin profile: Field remains editable for data correction | GIVEN standard user edits feedback WHEN viewing Submission_Date__c THEN field is read-only GIVEN System Admin edits feedback WHEN viewing Submission_Date__c THEN field is editable GIVEN user saves edited feedback WHEN Submission_Date__c unchanged THEN original date persists | Feedback__c | Feedback__c.Submission_Date__c
UC-004-03 | BR-004 | Generate feedback report by submission date | Business User | User runs feedback report for specific date range | 1. User navigates to Reports tab 2. User selects Feedback by Submission Date report 3. User sets date range filter on Submission_Date__c 4. User clicks Run Report 5. System displays feedback records within date range 6. System groups results by Submission_Date__c | 5a. If no records found: System displays 'No data available' message | GIVEN user filters by date range WHEN report runs THEN only feedback within range displays GIVEN report includes Submission_Date__c WHEN viewing results THEN date column is sortable GIVEN feedback exists WHEN grouping by Submission_Date__c THEN count per date is accurate | Feedback__c | Feedback__c.Submission_Date__c, Feedback__c.Id
UC-004-04 | BR-004 | Validate submission date on data import | System Admin | Admin imports feedback records via Data Loader | 1. Admin prepares CSV with feedback data including Submission_Date__c 2. Admin initiates Data Loader insert operation 3. System validates Submission_Date__c format for each row 4. System inserts records with valid dates 5. System generates error log for invalid date formats | 3a. If Submission_Date__c is blank: System populates with import date 3b. If date format invalid: System skips row and logs error | GIVEN CSV has valid dates WHEN import completes THEN all records inserted with correct Submission_Date__c GIVEN CSV has blank dates WHEN import completes THEN Submission_Date__c equals import date GIVEN CSV has invalid dates WHEN import completes THEN error log identifies failed rows | Feedback__c | Feedback__c.Submission_Date__c
UC-005-01 | BR-005 | Create Feedback Record with Account Association | Customer Service Rep | User clicks New on Feedback object | 1. User clicks New button on Feedback tab 2. System displays Feedback creation form with Account lookup field marked required 3. User searches and selects Account via lookup 4. User enters feedback details (Subject, Description, Rating) 5. User clicks Save 6. System validates Account is populated and saves Feedback record | 3a. If Account not found: User clicks New Account to create account first 6a. If Account field empty: System displays error 'Account is required' and prevents save | GIVEN user is on Feedback creation form WHEN Account field is empty and user clicks Save THEN system displays validation error GIVEN user selects valid Account WHEN user saves Feedback THEN Feedback__c.Account__c is populated with Account ID GIVEN Feedback record exists WHEN user views record THEN Account name displays as clickable link GIVEN Account is deleted WHEN user attempts to delete THEN system prevents deletion if related Feedback records exist | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Rating__c
UC-005-02 | BR-005 | View Account-Level Feedback Summary Report | Account Manager | User navigates to Feedback Reports tab | 1. User opens Feedback by Account report 2. System displays report grouped by Account name 3. User applies filters for date range or feedback rating 4. System refreshes report showing feedback count and average rating per Account 5. User clicks Account name to drill into detailed feedback records | 3a. If no feedback exists for date range: System displays 'No records to display' message | GIVEN Feedback records exist WHEN user runs report THEN each row displays Account name with feedback count GIVEN multiple Feedback records per Account WHEN report loads THEN system calculates average rating per Account GIVEN user filters by date range WHEN report refreshes THEN only Feedback within date range displays GIVEN user clicks Account name in report WHEN drill-through executes THEN related Feedback records display | Account, Feedback__c, Report | Feedback__c.Account__c, Feedback__c.Rating__c, Feedback__c.CreatedDate
UC-005-03 | BR-005 | Display Related Feedback on Account Page | Sales Rep | User opens Account record detail page | 1. User navigates to Account record 2. System displays Account detail page with Related Feedback list 3. User views feedback count and recent feedback entries 4. User clicks View All to see complete feedback history 5. System opens filtered Feedback list view for that Account | 3a. If no feedback exists: System displays 'No feedback records' message in related list | GIVEN Account has related Feedback WHEN user views Account page THEN Related Feedback list displays up to 10 recent records GIVEN user is on Account page WHEN user clicks New in Related Feedback THEN Feedback__c.Account__c auto-populates with current Account ID GIVEN Feedback records exist WHEN user clicks View All THEN system displays all Feedback filtered by Account GIVEN user lacks read access to Feedback WHEN Account page loads THEN Related Feedback section is hidden | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Subject__c, Feedback__c.CreatedDate
UC-005-04 | BR-005 | Bulk Import Feedback with Account Matching | System Administrator | Admin initiates Data Import Wizard for Feedback | 1. Admin prepares CSV with Feedback data including Account External ID 2. Admin opens Data Import Wizard and selects Feedback object 3. Admin maps CSV columns to Feedback fields and Account lookup via External ID 4. System validates all Account External IDs exist 5. System imports Feedback records and associates with matched Accounts 6. System displays import results with success and error counts | 4a. If Account External ID not found: System logs error and skips that row 4b. If Account field blank in CSV: System rejects row with validation error | GIVEN CSV contains valid Account External IDs WHEN import executes THEN Feedback__c.Account__c populates with matching Account ID GIVEN CSV row has blank Account field WHEN import runs THEN system skips row and logs validation error GIVEN 100 rows in CSV with 95 valid Accounts WHEN import completes THEN 95 records created and 5 errors logged GIVEN import completes WHEN admin views results THEN error file lists rows with missing or invalid Account references | Account, Feedback__c | Feedback__c.Account__c, Account.External_ID__c, Feedback__c.Subject__c, Feedback__c.Description__c
UC-006-01 | BR-006 | Calculate Average Rating on Feedback Creation | System | New Feedback record is created and linked to Account | 1. System detects new Feedback__c record inserted with Account lookup populated 2. System queries all Feedback__c records related to the Account 3. System calculates average of Feedback__c.Rating__c field values 4. System updates Account.Average_Rating__c with calculated value 5. System rounds result to two decimal places | 2a. If no Feedback records exist: set Account.Average_Rating__c to null 3a. If Rating__c is null on any record: exclude from calculation | GIVEN Account has 3 Feedback records with ratings 4, 5, 3 WHEN new Feedback is created THEN Account.Average_Rating__c = 4.00 GIVEN Account has no Feedback records WHEN last Feedback is deleted THEN Account.Average_Rating__c = null GIVEN Feedback has null Rating__c WHEN calculating average THEN System excludes null values from calculation GIVEN calculation completes WHEN viewing Account record THEN Average_Rating__c displays within 2 seconds | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-006-02 | BR-006 | Recalculate Average Rating on Feedback Update | System | Existing Feedback record Rating__c field is modified | 1. System detects Feedback__c.Rating__c field value changed 2. System identifies related Account via Feedback__c.Account__c lookup 3. System queries all Feedback__c records for that Account 4. System recalculates average of all Rating__c values 5. System updates Account.Average_Rating__c with new average | 1a. If Rating__c changed from value to null: recalculate excluding null 2a. If Account__c lookup is changed: recalculate for both old and new Account | GIVEN Account has Average_Rating__c = 4.00 WHEN Feedback Rating__c changes from 5 to 2 THEN Account.Average_Rating__c recalculates correctly GIVEN Feedback Rating__c changes WHEN update completes THEN Account.Average_Rating__c reflects new value immediately GIVEN Feedback moved to different Account WHEN Account__c lookup changes THEN both Accounts recalculate Average_Rating__c | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-006-03 | BR-006 | Recalculate Average Rating on Feedback Deletion | System | Feedback record is deleted from Account | 1. System detects Feedback__c record deletion 2. System captures Account__c lookup value before deletion 3. System queries remaining Feedback__c records for Account 4. System recalculates average from remaining Rating__c values 5. System updates Account.Average_Rating__c with new average | 3a. If no Feedback records remain: set Account.Average_Rating__c to null | GIVEN Account has 4 Feedback records with Average_Rating__c = 4.00 WHEN 1 Feedback is deleted THEN Account.Average_Rating__c recalculates from remaining 3 records GIVEN Account has 1 Feedback record WHEN that Feedback is deleted THEN Account.Average_Rating__c = null GIVEN Feedback is deleted WHEN deletion completes THEN Account.Average_Rating__c updates within 3 seconds | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-006-04 | BR-006 | Display Average Rating on Account Page | Business User | User navigates to Account record detail page | 1. User opens Account record 2. System displays Account.Average_Rating__c field on page layout 3. System shows value as read-only number field 4. System displays two decimal places or null if no ratings | 2a. If Average_Rating__c is null: display empty or '--' placeholder | GIVEN Account has Average_Rating__c = 4.25 WHEN User views Account THEN field displays '4.25' as read-only GIVEN Account has no Feedback records WHEN User views Account THEN Average_Rating__c displays as empty GIVEN User has read access to Account WHEN viewing record THEN Average_Rating__c is visible on page layout GIVEN User attempts to edit WHEN clicking Average_Rating__c field THEN System prevents manual editing | Account | Account.Average_Rating__c
UC-007-01 | BR-007 | Recalculate Account Average Rating on New Feedback | System | New Feedback__c record is created | 1. System detects new Feedback__c record creation 2. System retrieves associated Account via Feedback__c.Account__c lookup 3. System queries all related Feedback__c records for the Account 4. System calculates average of Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field 6. System commits transaction | 3a. If no other feedback exists: Set Account.Average_Rating__c to current feedback rating 4a. If Rating__c is null: Exclude from calculation and log error | GIVEN an Account with 2 existing feedbacks rated 4 and 5 WHEN a new feedback with rating 3 is submitted THEN Account.Average_Rating__c = 4.0 GIVEN an Account with no existing feedbacks WHEN first feedback with rating 5 is submitted THEN Account.Average_Rating__c = 5.0 GIVEN a new feedback is created WHEN calculation completes THEN Account.Average_Rating__c is updated within 5 seconds GIVEN a feedback with null Rating__c WHEN submitted THEN Account.Average_Rating__c excludes null value from calculation | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-007-02 | BR-007 | Recalculate Account Average Rating on Feedback Update | System | Existing Feedback__c record Rating__c field is updated | 1. System detects Feedback__c.Rating__c field change 2. System retrieves associated Account via Feedback__c.Account__c 3. System queries all related Feedback__c records for the Account 4. System recalculates average of all Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field | 1a. If Rating__c changed from null to value: Include in calculation 1b. If Rating__c changed from value to null: Exclude from calculation | GIVEN an Account with feedbacks rated 3, 4, 5 WHEN one feedback rating changes from 3 to 5 THEN Account.Average_Rating__c updates to 4.67 GIVEN a feedback rating is updated WHEN recalculation completes THEN Account.Average_Rating__c reflects new average GIVEN Rating__c changes to null WHEN recalculation runs THEN system excludes null rating from average | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-007-03 | BR-007 | Recalculate Account Average Rating on Feedback Deletion | System | Feedback__c record is deleted | 1. System detects Feedback__c record deletion 2. System retrieves associated Account from deleted record 3. System queries remaining Feedback__c records for the Account 4. System recalculates average of remaining Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field | 3a. If no remaining feedback exists: Set Account.Average_Rating__c to null or 0 | GIVEN an Account with feedbacks rated 2, 4, 6 WHEN feedback rated 2 is deleted THEN Account.Average_Rating__c updates to 5.0 GIVEN an Account with one feedback WHEN that feedback is deleted THEN Account.Average_Rating__c is set to null GIVEN a feedback is deleted WHEN recalculation completes THEN Account.Average_Rating__c excludes deleted feedback rating | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-007-04 | BR-007 | Handle Bulk Feedback Submission with Rating Recalculation | System | Multiple Feedback__c records created via data import or API | 1. System detects bulk Feedback__c record creation 2. System groups feedbacks by Account__c lookup field 3. System calculates average rating per Account in batch 4. System updates Account.Average_Rating__c for all affected Accounts 5. System processes within governor limits | 5a. If governor limits approached: Process in smaller batches asynchronously | GIVEN 200 feedbacks imported for 50 Accounts WHEN bulk insert completes THEN all 50 Account.Average_Rating__c fields are updated correctly GIVEN bulk feedback creation WHEN processing THEN system completes within Salesforce governor limits GIVEN multiple feedbacks for same Account WHEN created simultaneously THEN Account.Average_Rating__c reflects all new ratings | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-01 | BR-008 | Recalculate Account Average Rating on Feedback Update | System | Feedback__c.Rating__c field is modified | 1. System detects Rating__c field change on Feedback__c record 2. System queries all Feedback__c records related to parent Account 3. System calculates average of all Rating__c values 4. System updates Account.Average_Rating__c with calculated value 5. System commits transaction | 2a. If no other Feedback records exist: Set Account.Average_Rating__c to current Rating__c value 3a. If Rating__c is null on any record: Exclude from average calculation | GIVEN Account has 3 Feedback records with ratings 3, 4, 5 WHEN one rating changes from 4 to 2 THEN Account.Average_Rating__c updates to 3.33 GIVEN Account has 1 Feedback record with rating 5 WHEN rating changes to 3 THEN Account.Average_Rating__c updates to 3 GIVEN Account has 2 Feedback records with ratings 4 and null WHEN rating 4 changes to 2 THEN Account.Average_Rating__c calculates as 2 GIVEN Feedback rating changes WHEN calculation completes THEN Account.Average_Rating__c updates within same transaction | Account, Feedback__c | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-02 | BR-008 | Handle Bulk Feedback Rating Updates | System | Multiple Feedback__c records updated via Data Loader or API | 1. System detects bulk update of Rating__c on multiple Feedback__c records 2. System identifies unique parent Account IDs from updated records 3. System processes each Account once to recalculate average 4. System updates all affected Account.Average_Rating__c values 5. System completes bulk operation within governor limits | 3a. If updates exceed 200 Accounts: Process in batches to avoid CPU timeout 5a. If SOQL limit approached: Aggregate queries by Account to reduce query count | GIVEN 500 Feedback records updated across 50 Accounts WHEN bulk update executes THEN all 50 Account.Average_Rating__c values recalculate correctly GIVEN bulk update of Feedback records WHEN processing THEN system stays within SOQL query limits (max 100 queries) GIVEN multiple Feedback records for same Account updated WHEN calculation runs THEN Account average recalculates only once per transaction | Account, Feedback__c | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-03 | BR-008 | Validate Rating Value Before Recalculation | System | Feedback__c.Rating__c field value is changed | 1. System validates Rating__c is within acceptable range (1-5) 2. System confirms Account__c lookup field is populated 3. System proceeds with average rating recalculation 4. System updates Account.Average_Rating__c | 1a. If Rating__c is outside range or negative: Prevent save and display error message 2a. If Account__c is null: Skip recalculation and log error | GIVEN Feedback__c.Rating__c is set to 6 WHEN user saves THEN system prevents save with error 'Rating must be between 1 and 5' GIVEN Feedback__c.Rating__c is valid and Account__c is populated WHEN save occurs THEN recalculation executes successfully GIVEN Feedback__c.Account__c is null WHEN Rating__c changes THEN system skips recalculation without error | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-04 | BR-008 | Update Average Rating Precision and Rounding | System | Average rating calculation completes | 1. System calculates sum of all Rating__c values for Account 2. System divides sum by count of non-null Rating__c records 3. System rounds result to 2 decimal places 4. System updates Account.Average_Rating__c with rounded value | 2a. If count is zero: Set Account.Average_Rating__c to null | GIVEN Account has ratings 3, 4, 5 WHEN average calculates THEN Account.Average_Rating__c equals 4.00 GIVEN Account has ratings 3, 3, 5 WHEN average calculates THEN Account.Average_Rating__c equals 3.67 GIVEN all Feedback records deleted for Account WHEN recalculation runs THEN Account.Average_Rating__c sets to null | Account, Feedback__c | Feedback__c.Rating__c, Account.Average_Rating__c
UC-009-01 | BR-009 | Recalculate Account Rating on Feedback Deletion | System | Feedback__c record is deleted | 1. User deletes Feedback__c record 2. System captures deleted Feedback__c.Account__c lookup value 3. System queries remaining Feedback__c records for same Account 4. System calculates average of Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field 6. System commits transaction | 3a. If no remaining Feedback records exist: Set Account.Average_Rating__c to null 4a. If Rating__c is null on any record: Exclude from calculation | GIVEN Account has 3 Feedback records with ratings 4, 5, 3 WHEN user deletes Feedback with rating 5 THEN Account.Average_Rating__c = 3.5 GIVEN Account has 1 Feedback record WHEN user deletes that Feedback THEN Account.Average_Rating__c = null GIVEN Feedback deletion occurs WHEN recalculation completes THEN Account Last Modified Date is updated GIVEN bulk delete of 200 Feedback records WHEN deletion completes THEN all associated Accounts have updated Average_Rating__c | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Account__c, Feedback__c.Rating__c
UC-009-02 | BR-009 | Handle Feedback Deletion Without Account Association | System | Feedback__c record without Account lookup is deleted | 1. User deletes Feedback__c record 2. System checks Feedback__c.Account__c field 3. System identifies Account__c is null 4. System completes deletion without recalculation 5. System logs deletion event | 2a. If Account__c was populated but Account is deleted: Skip recalculation | GIVEN Feedback__c.Account__c is null WHEN user deletes Feedback THEN no Account record is updated GIVEN Feedback references deleted Account WHEN user deletes Feedback THEN deletion succeeds without error | Feedback__c, Account | Feedback__c.Account__c
UC-009-03 | BR-009 | Recalculate Multiple Accounts on Bulk Deletion | System | Multiple Feedback__c records deleted in bulk operation | 1. User selects and deletes multiple Feedback__c records 2. System collects unique Account__c IDs from deleted records 3. System queries remaining Feedback__c for each Account 4. System calculates average Rating__c per Account 5. System performs bulk update on Account.Average_Rating__c 6. System completes transaction within governor limits | 6a. If governor limits approached: Process Accounts in batches using Queueable Apex | GIVEN 50 Feedback records across 10 Accounts deleted WHEN bulk delete executes THEN all 10 Accounts have recalculated Average_Rating__c GIVEN bulk deletion WHEN processing completes THEN operation stays within SOQL query limits (100 queries) GIVEN bulk deletion WHEN processing completes THEN operation stays within DML row limits (10,000 rows) | Feedback__c, Account | Feedback__c.Account__c, Feedback__c.Rating__c, Account.Average_Rating__c
UC-010-01 | BR-010 | Submit New Customer Feedback from Account Page | Business User | User clicks 'New Feedback' button on Account page | 1. User clicks 'New Feedback' button on Account record page 2. System displays embedded feedback form component 3. User enters feedback details (Type, Category, Comments, Priority) 4. User clicks 'Submit' button 5. System validates required fields are populated 6. System creates Customer_Feedback__c record linked to Account | 5a. If required fields missing: System displays inline error messages, prevents submission 6a. If submission fails: System displays error toast notification with retry option | GIVEN user is on Account page WHEN user clicks 'New Feedback' button THEN feedback form displays without page navigation GIVEN user completes all required fields WHEN user clicks Submit THEN Customer_Feedback__c record is created with Account__c lookup populated GIVEN user submits form with missing required fields WHEN validation runs THEN inline error messages display and submission is blocked GIVEN feedback is successfully submitted WHEN record is created THEN success toast notification displays and form clears | Account, Customer_Feedback__c | Customer_Feedback__c.Account__c, Customer_Feedback__c.Feedback_Type__c, Customer_Feedback__c.Category__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Priority__c
UC-010-02 | BR-010 | Cancel Feedback Submission and Clear Form | Business User | User clicks 'Cancel' button on feedback form | 1. User begins entering feedback data in form 2. User clicks 'Cancel' button 3. System displays confirmation modal if data entered 4. User confirms cancellation 5. System clears all form fields and closes form | 3a. If no data entered: System immediately clears form without confirmation 4a. If user clicks 'Go Back' on modal: System returns to form with data intact | GIVEN user has entered data in form WHEN user clicks Cancel THEN confirmation modal displays GIVEN user confirms cancellation WHEN modal action completes THEN all form fields are cleared GIVEN user has not entered data WHEN user clicks Cancel THEN form clears immediately without confirmation | Customer_Feedback__c
UC-010-03 | BR-010 | Auto-populate Account Context in Feedback Form | System | Feedback form component loads on Account page | 1. User opens feedback form from Account record page 2. System retrieves current Account record ID from page context 3. System pre-populates Account__c lookup field with current Account 4. System displays Account Name as read-only reference 5. System disables Account__c field to prevent modification | 2a. If Account ID cannot be retrieved: System displays error message and disables form submission | GIVEN user opens form from Account page WHEN form loads THEN Account__c field is pre-populated with current Account ID GIVEN Account__c field is populated WHEN form displays THEN Account Name shows as read-only text GIVEN form is loaded WHEN user attempts to change Account THEN Account__c field is disabled and cannot be modified | Account, Customer_Feedback__c | Customer_Feedback__c.Account__c, Account.Name
UC-010-04 | BR-010 | View Feedback Confirmation and Record Details | Business User | Customer_Feedback__c record is successfully created | 1. System creates Customer_Feedback__c record 2. System displays success toast with feedback record number 3. System provides 'View Record' link in toast notification 4. User clicks 'View Record' link 5. System navigates to Customer_Feedback__c record detail page in new subtab | 3a. If user dismisses toast: Form clears and remains on Account page without navigation | GIVEN feedback record is created WHEN creation completes THEN success toast displays with record number GIVEN success toast displays WHEN user clicks 'View Record' THEN Customer_Feedback__c detail page opens in new subtab GIVEN success toast displays WHEN user dismisses toast THEN user remains on Account page with cleared form | Customer_Feedback__c, Account | Customer_Feedback__c.Name
UC-011-01 | BR-011 | Submit Feedback with Star Rating Selection | Business User | User opens feedback submission form | 1. User opens feedback submission form 2. System displays rating selector with 1-5 star options 3. User clicks on desired star rating (1-5) 4. System highlights selected rating and all stars up to selection 5. User completes remaining form fields 6. User clicks Submit button 7. System saves Feedback__c record with Rating__c field value | 3a. If user clicks different star rating: System updates selection and highlights new rating 6a. If no rating selected: System displays error 'Rating is required' and prevents submission | GIVEN user is on feedback form WHEN form loads THEN rating selector displays 5 clickable stars GIVEN user clicks 3-star rating WHEN selection is made THEN stars 1-3 are highlighted and Rating__c = 3 GIVEN user has not selected rating WHEN user clicks Submit THEN error message displays and form does not submit GIVEN user selects 5-star rating WHEN form is submitted THEN Feedback__c.Rating__c = 5 | Feedback__c | Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Submitted_Date__c
UC-011-02 | BR-011 | Change Star Rating Before Submission | Business User | User selects initial star rating then changes mind | 1. User selects initial star rating (e.g., 2 stars) 2. System highlights stars 1-2 3. User clicks different star rating (e.g., 4 stars) 4. System updates highlight to stars 1-4 5. User submits form 6. System saves Feedback__c with final Rating__c value | 3a. If user hovers over different star: System shows preview highlight without committing selection | GIVEN user selected 2-star rating WHEN user clicks 4-star rating THEN highlight updates to 4 stars and Rating__c = 4 GIVEN user changes rating multiple times WHEN form is submitted THEN only final rating value is saved GIVEN user hovers over star WHEN mouse moves away without clicking THEN previous selection remains unchanged | Feedback__c | Feedback__c.Rating__c
UC-011-03 | BR-011 | Display Visual Star Rating Indicator | Business User | User views feedback submission form | 1. User navigates to feedback form 2. System renders rating selector component 3. System displays 5 empty star icons in horizontal row 4. System shows label 'Select Rating (1-5 stars)' above selector 5. User hovers over star icon 6. System displays hover state with visual feedback | 5a. If user is on mobile device: System displays touch-optimized star icons with larger tap targets | GIVEN user views form WHEN page loads THEN 5 empty star icons display horizontally with equal spacing GIVEN user hovers over 3rd star WHEN mouse enters star area THEN stars 1-3 show hover state GIVEN user is on mobile WHEN form loads THEN star icons are minimum 44x44 pixels for touch accessibility GIVEN rating selector displays WHEN user views it THEN descriptive label is visible above stars | Feedback__c | Feedback__c.Rating__c
UC-012-01 | BR-012 | Submit Customer Feedback with Comments | Business User | User navigates to feedback submission form | 1. User opens feedback submission form 2. System displays form with text area for comments 3. User enters customer comments in text area 4. User clicks Submit button 5. System validates comment field is not empty 6. System creates Feedback__c record with comments | 5a. If comment field is empty: System displays error message 'Customer comments are required' 5b. If comment exceeds character limit: System displays error message 'Comments cannot exceed 32,000 characters' | GIVEN user is on feedback form WHEN form loads THEN text area for comments is visible and enabled GIVEN user enters valid comments WHEN user clicks Submit THEN Feedback__c record is created with Comments__c field populated GIVEN user submits empty comment WHEN user clicks Submit THEN error message displays and record is not created GIVEN user enters 32,000 characters WHEN user clicks Submit THEN record saves successfully | Feedback__c | Feedback__c.Comments__c, Feedback__c.Submitted_Date__c, Feedback__c.Submitted_By__c
UC-012-02 | BR-012 | Edit Customer Comments Before Submission | Business User | User enters text in comments text area | 1. User types customer comments in text area 2. System displays character count below text area 3. User edits or deletes text content 4. System updates character count in real-time 5. User completes editing and clicks Submit | 4a. If character count exceeds limit: System disables Submit button and highlights text area in red | GIVEN user types in text area WHEN each character is entered THEN character count updates immediately GIVEN user exceeds character limit WHEN typing continues THEN Submit button is disabled GIVEN user pastes text WHEN text is pasted THEN character count reflects total characters including pasted content | Feedback__c | Feedback__c.Comments__c
UC-012-03 | BR-012 | View Required Field Indicator for Comments | Business User | User opens feedback submission form | 1. User navigates to feedback form 2. System displays text area with red asterisk indicator 3. System displays label 'Customer Comments *' 4. User attempts to submit without entering comments 5. System displays validation error message | 4a. If user enters comments then deletes all text: System shows inline error 'This field is required' | GIVEN form loads WHEN user views comments field THEN red asterisk is visible next to field label GIVEN user submits empty form WHEN Submit is clicked THEN error message appears on comments field GIVEN user enters then clears comments WHEN field loses focus THEN inline validation error displays | Feedback__c | Feedback__c.Comments__c
UC-012-04 | BR-012 | Preserve Comments on Form Validation Error | Business User | User submits form with validation errors | 1. User enters customer comments in text area 2. User fills other required fields incorrectly 3. User clicks Submit button 4. System validates all fields and finds errors 5. System displays error messages and retains entered comments 6. User corrects errors and resubmits successfully | 5a. If session times out: System redirects to login and comments are lost | GIVEN user enters comments WHEN form validation fails THEN comments text remains in text area GIVEN validation errors occur WHEN user corrects errors THEN previously entered comments are still present GIVEN user enters comments WHEN page refreshes due to error THEN comments are preserved | Feedback__c | Feedback__c.Comments__c
UC-013-01 | BR-013 | Submit Feedback from Account Page with Auto-Link | Business User | User clicks Submit Feedback button on Account page | 1. User navigates to Account detail page 2. User clicks Submit Feedback button 3. System opens feedback submission modal with Account ID pre-populated 4. User enters feedback text and selects feedback type 5. User clicks Submit 6. System creates Feedback__c record with Account__c field populated | 4a. If feedback text is empty: System displays error message 'Feedback text is required' 6a. If Account ID is missing: System logs error and prevents submission | GIVEN user is on Account detail page WHEN user submits feedback THEN Feedback__c.Account__c equals current Account.Id GIVEN user submits feedback WHEN Feedback__c is created THEN user sees success message with feedback reference number GIVEN user leaves feedback text empty WHEN user clicks Submit THEN system displays validation error GIVEN feedback is submitted WHEN user views Account related list THEN new feedback appears in Account Feedback related list | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Feedback_Text__c, Feedback__c.Feedback_Type__c, Account.Id
UC-013-02 | BR-013 | Validate Account Context Before Feedback Submission | System | User attempts to submit feedback from Account page | 1. User clicks Submit on feedback form 2. System retrieves current Account.Id from page context 3. System validates Account record exists and is accessible 4. System validates user has read access to Account 5. System proceeds with feedback creation | 3a. If Account record does not exist: System displays error 'Account not found' and prevents submission 4a. If user lacks Account access: System displays error 'Insufficient privileges' and prevents submission | GIVEN Account is deleted WHEN user submits feedback THEN system prevents submission with error message GIVEN user lacks Account read access WHEN user attempts feedback submission THEN system displays insufficient privileges error GIVEN valid Account context WHEN system validates THEN feedback submission proceeds | Account, Feedback__c | Account.Id, Feedback__c.Account__c
UC-013-03 | BR-013 | Display Account Information in Feedback Form | Business User | User opens feedback submission form from Account page | 1. User clicks Submit Feedback button on Account page 2. System retrieves Account.Name and Account.AccountNumber 3. System displays feedback form with Account details in header 4. System disables Account lookup field to prevent manual changes 5. User views Account context while entering feedback | 2a. If Account data cannot be retrieved: System displays generic feedback form without Account context | GIVEN user opens feedback form from Account WHEN form loads THEN Account.Name displays in form header GIVEN feedback form is open WHEN user views Account lookup field THEN field is disabled and pre-populated GIVEN user submits feedback WHEN viewing confirmation THEN Account name appears in success message | Account, Feedback__c | Account.Name, Account.AccountNumber, Feedback__c.Account__c
UC-013-04 | BR-013 | Prevent Feedback Submission Without Account Context | System | User attempts to access feedback form outside Account page | 1. User navigates to Feedback__c object tab or home page 2. User clicks New Feedback button 3. System detects no Account context in URL parameters 4. System displays standard feedback form with Account lookup enabled 5. User manually selects Account from lookup field | 3a. If accessed from Account page: System auto-populates and locks Account__c field | GIVEN user creates feedback from Feedback tab WHEN form loads THEN Account lookup field is enabled and empty GIVEN user creates feedback from Account page WHEN form loads THEN Account lookup field is disabled and populated GIVEN no Account context exists WHEN user submits without selecting Account THEN system displays validation error | Feedback__c, Account | Feedback__c.Account__c
UC-014-01 | BR-014 | Display Success Message After Feedback Submission | Business User | User clicks Submit button on feedback form | 1. User completes feedback form fields 2. User clicks Submit button 3. System validates required fields are populated 4. System creates Feedback__c record 5. System displays success confirmation message 6. System clears form fields | 3a. If required fields missing: System displays field-level error messages and prevents submission 4a. If record creation fails: System displays error message with retry option | GIVEN user has completed all required fields WHEN user clicks Submit THEN success message displays within 2 seconds GIVEN feedback record is created WHEN submission completes THEN message includes confirmation text 'Your feedback has been successfully submitted' GIVEN success message displays WHEN user views screen THEN form fields are cleared and ready for new entry GIVEN submission fails WHEN error occurs THEN error message displays with specific failure reason | Feedback__c | Feedback__c.Status__c, Feedback__c.Submitted_Date__c, Feedback__c.Submitter__c
UC-014-02 | BR-014 | Send Email Confirmation After Feedback Submission | Business User | Feedback__c record is created with Status__c = 'Submitted' | 1. System creates Feedback__c record 2. System sets Feedback__c.Status__c to 'Submitted' 3. System retrieves submitter email from User record 4. System sends confirmation email to submitter 5. System updates Feedback__c.Confirmation_Sent__c to TRUE | 3a. If submitter email is blank: System logs error and skips email send 4a. If email send fails: System retries once after 5 minutes | GIVEN feedback record is created WHEN Status__c = 'Submitted' THEN confirmation email is sent within 1 minute GIVEN email is sent successfully WHEN process completes THEN Feedback__c.Confirmation_Sent__c = TRUE GIVEN email contains feedback details WHEN user receives email THEN email includes Feedback ID and submission timestamp GIVEN email send fails WHEN retry limit reached THEN system creates Task for admin review | Feedback__c, User, Task | Feedback__c.Status__c, Feedback__c.Confirmation_Sent__c, Feedback__c.Submitter__c, User.Email
UC-014-03 | BR-014 | Display Confirmation Banner with Record Details | Business User | Feedback__c record save completes successfully | 1. System saves Feedback__c record 2. System generates unique Feedback ID 3. System displays green success banner at top of page 4. Banner shows confirmation message with Feedback ID and timestamp 5. Banner auto-dismisses after 5 seconds | 5a. If user clicks X icon: Banner dismisses immediately | GIVEN record saves successfully WHEN page refreshes THEN green banner appears at top with success icon GIVEN banner displays WHEN user views message THEN text includes 'Feedback [ID] submitted successfully at [timestamp]' GIVEN banner appears WHEN 5 seconds elapse THEN banner fades out automatically GIVEN banner is visible WHEN user clicks dismiss icon THEN banner closes immediately | Feedback__c | Feedback__c.Name, Feedback__c.CreatedDate
UC-015-01 | BR-015 | Submit Feedback Form with All Required Fields | Business User | User clicks Submit button on feedback form | 1. User fills out feedback form fields 2. User clicks Submit button 3. System validates all required fields are populated 4. System saves feedback record to Feedback__c object 5. System displays success confirmation message 6. System clears form for new entry | 3a. If any required field is empty: System displays inline error message and prevents submission | GIVEN all required fields are completed WHEN user clicks Submit THEN feedback record is created successfully GIVEN all required fields are completed WHEN user clicks Submit THEN success message displays GIVEN required fields are completed WHEN submission succeeds THEN form clears to blank state | Feedback__c | Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Category__c, Feedback__c.Submitted_Date__c
UC-015-02 | BR-015 | Prevent Submission with Missing Required Fields | Business User | User clicks Submit button with incomplete required fields | 1. User partially fills out feedback form 2. User clicks Submit button 3. System validates required fields 4. System identifies empty required fields 5. System displays error message listing missing fields 6. System keeps form data intact for user correction | 5a. If only one field missing: System highlights specific field with red border and inline error text 5b. If multiple fields missing: System displays summary error at top and highlights all missing fields | GIVEN required field is empty WHEN user clicks Submit THEN submission is blocked and error displays GIVEN multiple required fields empty WHEN user clicks Submit THEN all missing fields are highlighted GIVEN validation fails WHEN error displays THEN existing form data is preserved GIVEN error displayed WHEN user fills missing field THEN error message clears dynamically | Feedback__c | Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Category__c
UC-015-03 | BR-015 | Display Real-Time Required Field Indicators | Business User | User opens feedback form | 1. User navigates to feedback form page 2. System loads form with all fields 3. System displays red asterisk next to required field labels 4. System shows helper text indicating required fields must be completed | 4a. If user focuses on required field then leaves it blank: System displays inline validation error immediately | GIVEN form loads WHEN user views form THEN all required fields show red asterisk indicator GIVEN user focuses on required field WHEN user leaves field blank THEN inline error appears immediately GIVEN required field has value WHEN user moves to next field THEN no error displays | Feedback__c | Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Category__c
UC-015-04 | BR-015 | Validate Field Format for Required Fields | Business User | User enters data in required field with format requirements | 1. User enters data in required field with specific format 2. User moves focus away from field or clicks Submit 3. System validates field is not empty 4. System validates data format matches requirements 5. System allows progression if both validations pass | 4a. If format invalid: System displays format error message with example of correct format 4b. If field empty: System displays required field error message | GIVEN required email field WHEN user enters invalid email format THEN format error displays and submission blocked GIVEN required phone field WHEN user enters non-numeric characters THEN format error displays GIVEN required field with valid format WHEN user clicks Submit THEN validation passes GIVEN format error displayed WHEN user corrects format THEN error clears and field shows valid state | Feedback__c | Feedback__c.Email__c, Feedback__c.Phone__c, Feedback__c.Subject__c
UC-016-01 | BR-016 | Prepare External Feedback Data for Migration | System Administrator | Admin receives 50 historical feedback records from external source | 1. Admin downloads feedback data from external source 2. Admin validates data format matches Salesforce import template 3. Admin maps external fields to Feedback__c object fields 4. Admin cleanses data (removes duplicates, formats dates) 5. Admin saves prepared CSV file for import | 2a. If data format invalid: Admin transforms data using Excel/data tool 4a. If duplicates found: Admin flags records for review before import | GIVEN external feedback file WHEN Admin validates format THEN all required fields are present GIVEN 50 records WHEN Admin checks for duplicates THEN duplicate records are identified GIVEN mapped data WHEN Admin reviews CSV THEN all fields match Feedback__c API names | Feedback__c | Feedback__c.External_ID__c, Feedback__c.Feedback_Date__c, Feedback__c.Feedback_Text__c, Feedback__c.Source__c
UC-016-02 | BR-016 | Import Historical Feedback Records via Data Loader | System Administrator | Admin initiates Data Loader import process | 1. Admin opens Salesforce Data Loader and logs in 2. Admin selects Insert operation for Feedback__c object 3. Admin uploads prepared CSV file with 50 records 4. Admin maps CSV columns to Feedback__c fields 5. System validates and imports all records 6. System generates success/error log file | 5a. If validation errors occur: System logs errors and skips failed records 5b. If duplicate External_ID__c detected: System prevents duplicate insert | GIVEN 50 valid records WHEN import completes THEN all 50 Feedback__c records are created GIVEN import process WHEN errors occur THEN error log identifies specific failed records GIVEN duplicate External_ID__c WHEN import runs THEN system prevents duplicate creation GIVEN successful import WHEN Admin queries Feedback__c THEN Source__c = 'Historical Migration' | Feedback__c | Feedback__c.External_ID__c, Feedback__c.Feedback_Date__c, Feedback__c.Feedback_Text__c, Feedback__c.Source__c, Feedback__c.Migrated_Date__c
UC-016-03 | BR-016 | Validate Migrated Feedback Data Integrity | System Administrator | Admin completes feedback data import | 1. Admin runs report on Feedback__c with filter Source__c = 'Historical Migration' 2. System displays count of migrated records 3. Admin verifies record count matches expected 50 records 4. Admin spot-checks 10 random records for data accuracy 5. Admin marks migration as complete in tracking document | 3a. If count mismatch: Admin reviews error log and re-imports failed records 4a. If data inaccuracies found: Admin updates records manually or re-imports | GIVEN migration complete WHEN Admin runs report THEN exactly 50 Feedback__c records exist with Source__c = 'Historical Migration' GIVEN spot-check WHEN Admin reviews 10 records THEN all field values match source data GIVEN validation complete WHEN Admin checks dates THEN all Feedback_Date__c values are valid historical dates | Feedback__c | Feedback__c.Source__c, Feedback__c.Feedback_Date__c, Feedback__c.External_ID__c, Feedback__c.Migrated_Date__c
UC-016-04 | BR-016 | Auto-Stamp Migration Metadata on Import | System | Feedback__c record created with Source__c = 'Historical Migration' | 1. System detects new Feedback__c record creation 2. System checks if Source__c = 'Historical Migration' 3. System populates Migrated_Date__c with today's date 4. System sets Is_Migrated__c = TRUE 5. System saves record with migration metadata | 2a. If Source__c is not 'Historical Migration': System skips migration metadata update | GIVEN new Feedback__c with Source__c = 'Historical Migration' WHEN record created THEN Migrated_Date__c = TODAY() GIVEN new Feedback__c with Source__c = 'Historical Migration' WHEN record created THEN Is_Migrated__c = TRUE GIVEN new Feedback__c with different Source__c WHEN record created THEN migration fields remain blank | Feedback__c | Feedback__c.Source__c, Feedback__c.Migrated_Date__c, Feedback__c.Is_Migrated__c
UC-017-01 | BR-017 | Download Standardized CSV Template for Feedback Import | System Administrator | Administrator navigates to feedback import configuration page | 1. Administrator clicks 'Download Template' button 2. System generates CSV template with predefined headers 3. System includes all required field mappings in header row 4. System downloads template file to administrator's device 5. Administrator opens template to verify structure | 2a. If template generation fails: display error message with retry option | GIVEN administrator is on import page WHEN clicks Download Template THEN CSV file downloads with correct headers GIVEN template is downloaded WHEN opened in Excel THEN all required feedback fields are present as column headers GIVEN template headers WHEN compared to Feedback__c object THEN all API field names match exactly GIVEN template file WHEN inspected THEN includes sample row with data format examples | Feedback__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Category__c
UC-017-02 | BR-017 | Validate CSV File Against Template Structure | System Administrator | Administrator uploads CSV file for feedback import | 1. Administrator selects CSV file and clicks Upload 2. System reads CSV file headers 3. System compares headers against template specification 4. System validates data types in each column 5. System displays validation summary with pass/fail status 6. System enables Import button if validation passes | 3a. If headers missing or incorrect: display specific missing/incorrect field names 4a. If data type mismatch found: highlight rows and columns with errors 5a. If validation fails: provide downloadable error report with line numbers | GIVEN CSV with correct headers WHEN uploaded THEN validation passes and Import button enables GIVEN CSV with missing required field WHEN uploaded THEN validation fails with specific field name in error message GIVEN CSV with invalid date format WHEN uploaded THEN system identifies exact row and column with error GIVEN validation errors exist WHEN administrator views results THEN error report shows line numbers and error descriptions | Feedback__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Category__c
UC-017-03 | BR-017 | Import Historical Feedback from Validated CSV | System Administrator | Administrator clicks Import button after successful validation | 1. Administrator clicks Import button 2. System maps CSV columns to Feedback__c fields 3. System creates Feedback__c records in batches 4. System tracks import progress with record count 5. System displays completion summary with success/failure counts 6. System sends email notification with import results | 3a. If record creation fails: log error and continue with remaining records 3b. If duplicate detected based on external ID: skip record and log warning 5a. If partial failure occurs: provide downloadable report of failed records | GIVEN validated CSV with 100 rows WHEN import executes THEN 100 Feedback__c records created successfully GIVEN import completes WHEN administrator views summary THEN total processed, success, and failure counts display accurately GIVEN import has failures WHEN administrator downloads error report THEN failed rows with error reasons are listed GIVEN import completes WHEN administrator checks email THEN notification contains import statistics and timestamp | Feedback__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Category__c, Feedback__c.External_ID__c, Feedback__c.Import_Batch_ID__c
UC-017-04 | BR-017 | Map Custom CSV Fields to Feedback Object | System Administrator | Administrator needs to import feedback with non-standard field names | 1. Administrator uploads CSV with custom headers 2. System displays field mapping interface 3. Administrator maps each CSV column to Feedback__c field 4. Administrator saves custom mapping configuration 5. System validates mapping completeness 6. System applies mapping to proceed with import | 5a. If required fields unmapped: display error and highlight missing mappings 4a. If administrator wants to reuse mapping: save as named template for future imports | GIVEN CSV with custom headers WHEN mapping interface opens THEN all CSV columns display with dropdown of Feedback__c fields GIVEN administrator maps all required fields WHEN saves configuration THEN mapping validation passes GIVEN required field unmapped WHEN administrator attempts to proceed THEN error message identifies unmapped required field GIVEN custom mapping saved WHEN administrator imports next file THEN saved mapping available for selection | Feedback__c, Field_Mapping_Template__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Field_Mapping_Template__c.Name, Field_Mapping_Template__c.Mapping_JSON__c
UC-018-01 | BR-018 | Validate Required Fields During Feedback Import | Data Migration Admin | Admin initiates feedback data import via Data Loader | 1. Admin uploads CSV file containing feedback records 2. System validates all required fields are populated 3. System checks field data types match schema 4. System validates picklist values against defined values 5. System creates Feedback__c records for valid rows 6. System generates import summary report | 2a. If required field missing: reject row and log error with row number 3a. If data type mismatch: reject row and specify expected format 4a. If invalid picklist value: reject row and list valid options | GIVEN feedback import file WHEN required field is blank THEN row is rejected with specific error message GIVEN feedback import file WHEN all required fields populated THEN record is created successfully GIVEN feedback import file WHEN picklist value not in defined list THEN row is rejected with valid values displayed GIVEN import completion WHEN errors exist THEN error log CSV is generated with row numbers and reasons | Feedback__c | Feedback__c.Customer_Name__c, Feedback__c.Feedback_Date__c, Feedback__c.Category__c, Feedback__c.Rating__c, Feedback__c.Comments__c
UC-018-02 | BR-018 | Validate Business Rules for Feedback Ratings | Data Migration Admin | Feedback record insert during migration | 1. System receives Feedback__c record for insert 2. System validates Rating__c is between 1 and 5 3. System validates Feedback_Date__c is not future date 4. System validates Comments__c length does not exceed 32000 characters 5. System inserts record if all validations pass | 2a. If Rating__c outside 1-5 range: reject with valid range message 3a. If Feedback_Date__c is future date: reject with date constraint error 4a. If Comments__c exceeds limit: truncate or reject based on configuration | GIVEN Rating__c value of 0 or 6 WHEN record inserted THEN validation error prevents insert GIVEN Feedback_Date__c in future WHEN record inserted THEN error message displays date must be today or earlier GIVEN Comments__c with 32001 characters WHEN record inserted THEN validation error prevents insert GIVEN all business rules satisfied WHEN record inserted THEN Feedback__c record created successfully | Feedback__c | Feedback__c.Rating__c, Feedback__c.Feedback_Date__c, Feedback__c.Comments__c
UC-018-03 | BR-018 | Validate Feedback Relationship to Account Records | Data Migration Admin | Feedback record with Account lookup during import | 1. System receives Feedback__c record with Account_ID__c value 2. System queries Account object for matching record 3. System validates Account exists and is active 4. System populates Feedback__c.Account__c lookup field 5. System inserts Feedback__c record with valid relationship | 2a. If Account_ID__c not found: reject row and log missing Account ID 3a. If Account is inactive: reject row and specify Account must be active 1a. If Account_ID__c is blank and Account required: reject row with missing relationship error | GIVEN Account_ID__c matches existing Account WHEN Feedback imported THEN Feedback__c.Account__c lookup is populated GIVEN Account_ID__c does not exist WHEN Feedback imported THEN record rejected with Account not found error GIVEN Account.IsActive__c is false WHEN Feedback imported THEN record rejected with inactive Account error GIVEN valid Account relationship WHEN import completes THEN Feedback visible on Account related list | Feedback__c, Account | Feedback__c.Account__c, Feedback__c.Account_ID__c, Account.Id, Account.IsActive__c
UC-018-04 | BR-018 | Validate Duplicate Feedback Prevention Rules | Data Migration Admin | Feedback record insert with potential duplicate | 1. System receives Feedback__c record for insert 2. System checks for existing records with same Account__c and Feedback_Date__c 3. System compares Customer_Email__c if provided 4. System allows insert if no duplicate found 5. System logs successful unique record creation | 2a. If duplicate found based on Account and Date: reject with duplicate error message 3a. If Customer_Email__c matches existing record: flag as potential duplicate and require admin review 2b. If duplicate detection rule configured as warning only: allow insert and create duplicate alert | GIVEN Feedback with same Account__c and Feedback_Date__c exists WHEN new record imported THEN duplicate error prevents insert GIVEN Feedback with same Customer_Email__c exists WHEN new record imported THEN admin receives duplicate alert GIVEN unique Feedback record WHEN imported THEN record created without duplicate warnings GIVEN duplicate detection WHEN error occurs THEN error log includes existing record ID for reference | Feedback__c | Feedback__c.Account__c, Feedback__c.Feedback_Date__c, Feedback__c.Customer_Email__c
UC-018-05 | BR-018 | Generate Data Quality Report Post-Import | Data Migration Admin | Feedback import batch completion | 1. System completes feedback import batch processing 2. System calculates total records processed, successful, and failed 3. System categorizes errors by validation type 4. System generates Data_Quality_Report__c record with metrics 5. System sends email notification to admin with report link | 2a. If zero records processed: send alert for empty import file 4a. If error rate exceeds 10%: flag report as requiring immediate review | GIVEN import batch completes WHEN processing finishes THEN Data_Quality_Report__c record created with accurate counts GIVEN validation errors occurred WHEN report generated THEN errors grouped by type with counts GIVEN import completion WHEN report ready THEN admin receives email with downloadable error log GIVEN error rate above 10% WHEN report generated THEN Report_Status__c set to 'Requires Review' | Data_Quality_Report__c, Feedback__c | Data_Quality_Report__c.Total_Records__c, Data_Quality_Report__c.Successful_Records__c, Data_Quality_Report__c.Failed_Records__c, Data_Quality_Report__c.Error_Rate__c, Data_Quality_Report__c.Report_Status__c
UC-019-01 | BR-019 | Recalculate Account Ratings After Feedback Migration | System Administrator | Feedback data migration batch job completes successfully | 1. System identifies all Accounts linked to migrated Feedback__c records 2. System retrieves all Feedback__c records per Account including newly migrated data 3. System calculates average rating from Feedback__c.Rating__c field 4. System updates Account.Average_Rating__c with calculated value 5. System logs recalculation timestamp in Account.Rating_Last_Calculated__c 6. System sends completion notification to administrator | 3a. If no Feedback__c records exist: Set Account.Average_Rating__c to null 4a. If Account update fails: Log error and continue with next Account 6a. If recalculation affects >1000 Accounts: Send summary report via email | GIVEN historical Feedback__c records are migrated WHEN recalculation runs THEN Account.Average_Rating__c reflects all feedback including migrated data GIVEN Account has 3 existing and 2 migrated Feedback__c records WHEN recalculation completes THEN Account.Average_Rating__c equals average of all 5 ratings GIVEN migration imports 500 Feedback__c records WHEN recalculation completes THEN all affected Accounts show updated Account.Rating_Last_Calculated__c timestamp GIVEN recalculation fails for specific Account WHEN error occurs THEN error is logged and process continues for remaining Accounts | Account, Feedback__c | Account.Average_Rating__c, Account.Rating_Last_Calculated__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-019-02 | BR-019 | Validate Feedback Data Before Recalculation | Data Migration Specialist | User initiates pre-recalculation validation check | 1. User clicks 'Validate Migrated Data' button on custom migration dashboard 2. System validates Feedback__c.Rating__c values are between 1-5 3. System checks all Feedback__c.Account__c lookups reference valid Accounts 4. System generates validation report showing errors and warnings 5. System displays report on dashboard with pass/fail status | 2a. If invalid ratings found: Flag records in validation report 3a. If orphaned Feedback__c records found: List in report for manual review 5a. If validation fails: Prevent recalculation process from starting | GIVEN migrated Feedback__c has Rating__c = 7 WHEN validation runs THEN record is flagged as invalid in report GIVEN Feedback__c.Account__c references deleted Account WHEN validation runs THEN record is listed as orphaned GIVEN validation finds errors WHEN validation completes THEN recalculation button remains disabled GIVEN all validations pass WHEN validation completes THEN recalculation button becomes enabled | Feedback__c, Account, Migration_Validation_Log__c | Feedback__c.Rating__c, Feedback__c.Account__c, Migration_Validation_Log__c.Status__c, Migration_Validation_Log__c.Error_Details__c
UC-019-03 | BR-019 | Monitor Recalculation Progress in Real-Time | System Administrator | Recalculation batch job starts execution | 1. System creates Recalculation_Job__c record with status 'In Progress' 2. System updates Recalculation_Job__c.Accounts_Processed__c after each batch 3. System updates Recalculation_Job__c.Errors_Encountered__c when failures occur 4. User refreshes custom monitoring dashboard to view progress 5. System updates Recalculation_Job__c.Status__c to 'Completed' when finished | 3a. If error count exceeds threshold: System pauses job and alerts administrator 5a. If job fails: System sets Status__c to 'Failed' and logs error details | GIVEN recalculation processes 100 Accounts WHEN user views dashboard THEN Recalculation_Job__c.Accounts_Processed__c shows 100 GIVEN 5 Account updates fail WHEN batch continues THEN Recalculation_Job__c.Errors_Encountered__c equals 5 GIVEN job completes successfully WHEN final batch finishes THEN Recalculation_Job__c.Status__c = 'Completed' GIVEN error count reaches 50 WHEN threshold exceeded THEN job pauses and admin receives email alert | Recalculation_Job__c, Account | Recalculation_Job__c.Status__c, Recalculation_Job__c.Accounts_Processed__c, Recalculation_Job__c.Errors_Encountered__c, Recalculation_Job__c.Started_Date__c, Recalculation_Job__c.Completed_Date__c
UC-019-04 | BR-019 | Handle Accounts with No Feedback Data | Automated System Process | Recalculation encounters Account with zero Feedback__c records | 1. System queries Feedback__c records for Account 2. System detects zero related Feedback__c records 3. System sets Account.Average_Rating__c to null 4. System sets Account.Feedback_Count__c to 0 5. System updates Account.Rating_Last_Calculated__c with current timestamp | 2a. If Feedback__c records exist but all have null Rating__c: Treat as zero feedback scenario | GIVEN Account has no Feedback__c records WHEN recalculation runs THEN Account.Average_Rating__c is set to null GIVEN Account has no Feedback__c records WHEN recalculation runs THEN Account.Feedback_Count__c equals 0 GIVEN Account previously had ratings but all Feedback__c deleted WHEN recalculation runs THEN Account.Average_Rating__c changes from previous value to null | Account, Feedback__c | Account.Average_Rating__c, Account.Feedback_Count__c, Account.Rating_Last_Calculated__c, Feedback__c.Rating__c
UC-020-01 | BR-020 | View Feedback Related List on Account | Business User | User navigates to Account record page | 1. User opens Account record page 2. System displays Feedback related list component 3. System queries all Feedback__c records where Feedback__c.Account__c = Current Account Id 4. System displays feedback records with key fields in list view 5. User views feedback records without leaving Account page | 3a. If no feedback records exist: Display 'No feedback records to display' message 3b. If user lacks read permission on Feedback__c: Hide related list component | GIVEN Account has 5 feedback records WHEN User opens Account page THEN All 5 feedback records display in related list GIVEN Account has no feedback records WHEN User opens Account page THEN Related list shows empty state message GIVEN User lacks Feedback__c read access WHEN User opens Account page THEN Feedback related list is not visible GIVEN Feedback related list is visible WHEN User views list THEN Feedback__c.Name, Feedback__c.Status__c, Feedback__c.CreatedDate display | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Name, Feedback__c.Status__c, Feedback__c.CreatedDate
UC-020-02 | BR-020 | Navigate to Feedback Record from Account | Business User | User clicks feedback record link in related list | 1. User views Feedback related list on Account page 2. User clicks Feedback__c.Name hyperlink 3. System navigates to Feedback__c record detail page 4. User views full feedback record details | 2a. If user clicks row action menu: Display available actions (Edit, Delete, View) 3a. If record is deleted before navigation: Display error toast 'Record no longer exists' | GIVEN User is on Account page WHEN User clicks feedback record name THEN System opens Feedback__c record page GIVEN User clicks feedback record WHEN Navigation completes THEN Correct Feedback__c record displays GIVEN Feedback record is deleted WHEN User attempts to open THEN Error message displays and user remains on Account page | Account, Feedback__c | Feedback__c.Id, Feedback__c.Name
UC-020-03 | BR-020 | Filter and Sort Feedback Records | Business User | User applies filter or sort on Feedback related list | 1. User views Feedback related list on Account page 2. User clicks column header to sort or applies list view filter 3. System re-queries Feedback__c records with sort/filter criteria 4. System refreshes related list with filtered/sorted results 5. User views updated feedback list | 3a. If filter returns no results: Display 'No items to display' message 2a. If user selects different list view: System applies predefined filter criteria | GIVEN 10 feedback records exist WHEN User sorts by CreatedDate descending THEN Records display newest first GIVEN User applies Status filter WHEN Filter = 'Open' THEN Only feedback records with Status__c = 'Open' display GIVEN User selects 'Recent Feedback' list view WHEN View loads THEN Only records from last 30 days display | Account, Feedback__c | Feedback__c.Status__c, Feedback__c.CreatedDate, Feedback__c.Account__c
UC-020-04 | BR-020 | Create New Feedback from Account Page | Business User | User clicks New button on Feedback related list | 1. User clicks New button in Feedback related list 2. System opens Feedback__c record creation modal 3. System pre-populates Feedback__c.Account__c with current Account Id 4. User enters required fields and clicks Save 5. System creates Feedback__c record and refreshes related list 6. User sees new feedback record in related list | 4a. If required fields missing: Display validation error and prevent save 4b. If user clicks Cancel: Close modal without saving and return to Account page | GIVEN User clicks New on Feedback related list WHEN Modal opens THEN Feedback__c.Account__c is pre-populated with current Account Id GIVEN User enters all required fields WHEN User clicks Save THEN New Feedback__c record is created and related list refreshes GIVEN User omits required field WHEN User clicks Save THEN Validation error displays and record is not created GIVEN New feedback is created WHEN Related list refreshes THEN New record appears at top of list | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Name, Feedback__c.Status__c, Feedback__c.Description__c

## Marcus - WBS
Phase | Task ID | Task Name | Description | Assigned Agent | Effort (days) | Dependencies | Deliverables | Validation Criteria
Parse error: Invalid control character at: line 1256 column 8 (char 63351)

## Marcus - Gap Analysis
Gap ID | Category | Current State | Target State | Gap Description | Priority | Effort | Dependencies
Parse error: Expecting value: line 1 column 1 (char 0)

## Marcus - Solution
Raw content (parse error: Expecting value: line 1 column 1 (char 0))

## Elena - QA
QA Specifications (raw)

## Jordan - DevOps
DevOps Specifications

## Aisha - Data
Data Specifications

## Lucas - Training
Training Specifications