## Dashboard
EXECUTION #116 - Digital Humans Test
Agent | Deliverable | Count/Size | Status
Sophie (PM) | Business Requirements | 20 BRs | ✅
Olivia (BA) | Use Cases | 78 UCs | ✅
Marcus (Architect) | As-Is Analysis | 6.8 KB | ✅
Marcus (Architect) | Gap Analysis | 25 KB | ✅
Marcus (Architect) | Solution Design | 19 KB | ✅
Marcus (Architect) | WBS | 84 KB | ✅
Elena (QA) | QA Specifications | 20.7 KB | ✅
Jordan (DevOps) | DevOps Specifications | 40 KB | ✅
Aisha (Data) | Data Specifications | 18 KB | ✅
Lucas (Trainer) | Training Specifications | 16.8 KB | ✅

## Sophie - BRs (20)
BR ID | Category | Requirement | Priority | Status
BR-001 | DATA_MODEL | The system must store customer feedback records with rating, comments, date, and association to a customer account. | SHOULD | VALIDATED
BR-002 | DATA_MODEL | Customer ratings must be captured using a standardized 1 to 5 star scale for consistency in measurement and reporting. | SHOULD | VALIDATED
BR-003 | DATA_MODEL | The system must allow customers to provide free-text comments along with their rating to capture qualitative feedback. | SHOULD | VALIDATED
BR-004 | DATA_MODEL | Each feedback record must capture the date when the feedback was submitted for tracking and reporting purposes. | SHOULD | VALIDATED
BR-005 | DATA_MODEL | Each feedback record must be associated with a specific customer account to enable account-level analysis and reporting. | SHOULD | VALIDATED
BR-006 | DATA_MODEL | Each customer account must have a field to store the calculated average rating from all associated feedback records. | SHOULD | VALIDATED
BR-007 | AUTOMATION | When a new feedback is submitted, the system must automatically recalculate the average rating for the associated account. | SHOULD | VALIDATED
BR-008 | AUTOMATION | When an existing feedback rating is modified, the system must automatically recalculate the average rating for the associated account. | SHOULD | VALIDATED
BR-009 | AUTOMATION | When a feedback record is deleted, the system must automatically recalculate the average rating for the associated account. | SHOULD | VALIDATED
BR-010 | UI_UX | Users must have access to a form interface on the account page to submit new customer feedback without navigating away. | SHOULD | VALIDATED
BR-011 | UI_UX | The feedback submission form must include a rating selector allowing users to choose a rating from 1 to 5 stars. | SHOULD | VALIDATED
BR-012 | UI_UX | The feedback submission form must include a text area for users to enter customer comments. | SHOULD | VALIDATED
BR-013 | UI_UX | When submitting feedback from an account page, the system must automatically link the feedback to that account. | SHOULD | VALIDATED
BR-014 | UI_UX | The system must confirm to the user when a feedback record has been successfully submitted. | SHOULD | VALIDATED
BR-015 | UI_UX | The feedback form must validate that required fields are completed before allowing submission. | SHOULD | VALIDATED
BR-016 | DATA_MODEL | The system must support migration of 50 historical feedback records from an external source into the new feedback structure. | SHOULD | VALIDATED
BR-017 | DATA_MODEL | A standardized CSV template must be provided to facilitate the import of historical feedback data with correct field mapping. | SHOULD | VALIDATED
BR-018 | DATA_MODEL | The migration process must validate that imported feedback data meets all business rules and data quality standards. | SHOULD | VALIDATED
BR-019 | AUTOMATION | After historical feedback data is migrated, all affected account average ratings must be recalculated to reflect the imported data. | SHOULD | VALIDATED
BR-020 | UI_UX | Users should be able to view all feedback records associated with an account from the account page. | SHOULD | VALIDATED

## Olivia - UCs (78)
UC ID | Parent BR | Title | Actor | Trigger | Main Flow | Alt Flows | Acceptance Criteria | SF Objects | SF Fields
UC-001-01 | BR-001 | Create Customer Feedback Record | Business User | User clicks New on Customer Feedback related list | 1. User clicks New on Customer_Feedback__c related list from Account 2. User enters Rating__c (1-5), Comments__c, and Feedback_Date__c 3. System auto-populates Account__c lookup with parent Account 4. User clicks Save 5. System validates required fields are populated 6. System creates Customer_Feedback__c record linked to Account | 5a. If Rating__c is blank: System displays error 'Rating is required' 5b. If Feedback_Date__c is future date: System displays error 'Feedback date cannot be in future' | GIVEN user is on Account record WHEN user creates feedback with valid data THEN Customer_Feedback__c record is created with Account__c populated GIVEN user submits feedback WHEN Rating__c is blank THEN error message displays and record is not saved GIVEN user enters future date WHEN user clicks Save THEN error message displays for Feedback_Date__c GIVEN feedback is saved WHEN user views Account THEN new feedback appears in related list | Account, Customer_Feedback__c | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Feedback_Date__c, Customer_Feedback__c.Account__c
UC-001-02 | BR-001 | Edit Existing Customer Feedback | Business User | User clicks Edit on Customer_Feedback__c record | 1. User opens Customer_Feedback__c record and clicks Edit 2. User modifies Rating__c or Comments__c fields 3. User clicks Save 4. System validates modified data 5. System updates Customer_Feedback__c record with timestamp | 4a. If Rating__c is outside 1-5 range: System displays error 'Rating must be between 1 and 5' 4b. If Account__c lookup is removed: System displays error 'Account association is required' | GIVEN existing feedback record WHEN user updates Rating__c or Comments__c THEN changes are saved successfully GIVEN user edits feedback WHEN Rating__c is invalid THEN error message displays and changes are not saved GIVEN user edits feedback WHEN Account__c is removed THEN error prevents saving GIVEN feedback is updated WHEN save is successful THEN LastModifiedDate is updated | Customer_Feedback__c, Account | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Account__c, Customer_Feedback__c.LastModifiedDate
UC-001-03 | BR-001 | View Customer Feedback on Account | Business User | User opens Account record | 1. User navigates to Account record 2. User scrolls to Customer Feedback related list 3. System displays all Customer_Feedback__c records linked to Account 4. User views Rating__c, Comments__c, and Feedback_Date__c in list view | 3a. If no feedback exists: System displays 'No records to display' message | GIVEN Account has feedback records WHEN user views Account THEN all related Customer_Feedback__c records display in related list GIVEN Account has no feedback WHEN user views Account THEN related list shows no records message GIVEN multiple feedback records exist WHEN user views list THEN records are sorted by Feedback_Date__c descending | Account, Customer_Feedback__c | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Feedback_Date__c, Customer_Feedback__c.Account__c
UC-001-04 | BR-001 | Delete Customer Feedback Record | Business User | User clicks Delete on Customer_Feedback__c record | 1. User opens Customer_Feedback__c record 2. User clicks Delete button 3. System displays confirmation dialog 4. User confirms deletion 5. System moves record to Recycle Bin 6. System removes record from Account related list | 4a. If user cancels: System returns to record detail page without deletion | GIVEN user has delete permission WHEN user confirms deletion THEN Customer_Feedback__c record moves to Recycle Bin GIVEN user deletes feedback WHEN deletion completes THEN record no longer appears on Account related list GIVEN user cancels deletion WHEN cancel is clicked THEN record remains unchanged | Customer_Feedback__c, Account | Customer_Feedback__c.IsDeleted, Customer_Feedback__c.Account__c
UC-002-01 | BR-002 | Capture Customer Rating on Account Record | Sales Rep | Sales Rep completes customer interaction and needs to record satisfaction rating | 1. Sales Rep opens Account record 2. Sales Rep clicks Edit on Account detail page 3. Sales Rep selects rating value from Customer_Rating__c picklist (1-5 stars) 4. Sales Rep clicks Save 5. System validates rating is between 1-5 6. System saves Account record with Customer_Rating__c populated | 3a. If Sales Rep leaves Customer_Rating__c blank: System allows save (rating is optional) 5a. If invalid value entered: System displays error 'Rating must be 1-5 stars' | GIVEN Sales Rep is on Account edit page WHEN they select a rating from 1-5 THEN Customer_Rating__c field saves selected value GIVEN Sales Rep selects rating value WHEN they click Save THEN only values 1, 2, 3, 4, or 5 are accepted GIVEN Account record exists WHEN Customer_Rating__c is populated THEN rating displays as star icons on Account detail page GIVEN multiple users access Account WHEN viewing Customer_Rating__c THEN all users see consistent 1-5 scale | Account | Account.Customer_Rating__c
UC-002-02 | BR-002 | Generate Customer Rating Report by Segment | Business Analyst | Business Analyst needs monthly customer satisfaction metrics | 1. Business Analyst navigates to Reports tab 2. Business Analyst creates new Account report 3. Business Analyst adds Customer_Rating__c field to report columns 4. Business Analyst groups report by Account.Type or Account.Industry 5. Business Analyst adds average formula for Customer_Rating__c 6. System calculates average rating per segment and displays results | 3a. If Customer_Rating__c is null for some records: System excludes null values from average calculation 6a. If no ratings exist for segment: System displays 0 or N/A | GIVEN Account records have Customer_Rating__c populated WHEN Business Analyst runs report THEN average rating calculates correctly (sum/count) GIVEN report includes Customer_Rating__c WHEN grouped by segment THEN each segment shows separate average rating GIVEN Accounts with null ratings exist WHEN calculating average THEN null values are excluded from calculation GIVEN report is saved WHEN other users access it THEN rating scale displays consistently as 1-5 | Account | Account.Customer_Rating__c, Account.Type, Account.Industry
UC-002-03 | BR-002 | Validate Rating Scale on Case Feedback | Support Agent | Support Agent closes Case and requests customer feedback rating | 1. Support Agent changes Case.Status to 'Closed' 2. Support Agent navigates to Case Feedback section 3. Support Agent enters Case_Feedback_Rating__c value (1-5 stars) 4. System validates rating is numeric and within 1-5 range 5. System saves Case record with Case_Feedback_Rating__c 6. System updates related Account.Customer_Rating__c with latest feedback average | 4a. If rating is outside 1-5 range: System displays error 'Please enter rating between 1 and 5 stars' 6a. If multiple Case ratings exist for Account: System calculates rolling average of last 10 Case ratings | GIVEN Support Agent enters Case feedback WHEN rating is 1-5 THEN Case_Feedback_Rating__c saves successfully GIVEN Support Agent enters invalid rating WHEN value is <1 or >5 THEN System prevents save and shows error message GIVEN Case is closed with rating WHEN Case_Feedback_Rating__c is saved THEN related Account.Customer_Rating__c updates automatically GIVEN Account has multiple Case ratings WHEN new rating is added THEN Account rating reflects average of recent feedback | Case, Account | Case.Status, Case.Case_Feedback_Rating__c, Account.Customer_Rating__c
UC-002-04 | BR-002 | Display Rating History on Account Timeline | Account Manager | Account Manager reviews customer satisfaction trends over time | 1. Account Manager opens Account record 2. Account Manager scrolls to Activity Timeline or Related List 3. System displays Customer_Rating_History__c records chronologically 4. Account Manager views Rating_Value__c (1-5), Rating_Date__c, and Rating_Source__c for each entry 5. Account Manager identifies rating trends (improving/declining) | 3a. If no rating history exists: System displays 'No ratings recorded' message 5a. If Account Manager needs detailed analysis: Account Manager exports rating history to Excel | GIVEN Account has rating history WHEN Account Manager views timeline THEN all Customer_Rating_History__c records display with 1-5 star values GIVEN multiple ratings exist WHEN displayed on timeline THEN records sort by Rating_Date__c descending (newest first) GIVEN rating history record exists WHEN viewed THEN Rating_Value__c shows only values 1, 2, 3, 4, or 5 GIVEN Account Manager reviews trends WHEN comparing ratings THEN consistent 1-5 scale enables accurate comparison | Account, Customer_Rating_History__c | Customer_Rating_History__c.Rating_Value__c, Customer_Rating_History__c.Rating_Date__c, Customer_Rating_History__c.Rating_Source__c, Customer_Rating_History__c.Account__c
UC-003-01 | BR-003 | Customer Submits Rating with Text Comment | Customer | Customer completes rating selection and enters comment text | 1. Customer selects rating value (1-5 stars) 2. Customer enters free-text comment in Comment__c field 3. Customer clicks Submit button 4. System validates comment length does not exceed 32,000 characters 5. System creates Customer_Feedback__c record with Rating__c and Comment__c populated 6. System displays confirmation message to customer | 2a. If customer leaves comment blank: System allows submission with null Comment__c value 4a. If comment exceeds character limit: System displays error 'Comment must be 32,000 characters or less' | GIVEN customer has selected a rating WHEN customer enters comment and clicks Submit THEN Customer_Feedback__c record is created with both Rating__c and Comment__c populated GIVEN customer has selected a rating WHEN customer leaves comment blank and clicks Submit THEN Customer_Feedback__c record is created with Rating__c populated and Comment__c null GIVEN customer enters 32,001 characters in comment WHEN customer clicks Submit THEN system displays character limit error and prevents submission GIVEN customer submits valid rating and comment WHEN submission completes THEN system displays 'Thank you for your feedback' confirmation | Customer_Feedback__c | Customer_Feedback__c.Rating__c, Customer_Feedback__c.Comment__c, Customer_Feedback__c.Customer__c, Customer_Feedback__c.Submission_Date__c
UC-003-02 | BR-003 | Customer Edits Existing Feedback Comment | Customer | Customer navigates to previously submitted feedback record | 1. Customer opens existing Customer_Feedback__c record 2. Customer clicks Edit button on Comment__c field 3. Customer modifies comment text 4. Customer clicks Save button 5. System updates Comment__c field value 6. System updates Last_Modified_Date__c timestamp | 1a. If feedback record is older than 30 days: System displays 'Editing not allowed for submissions older than 30 days' and disables Edit button 3a. If customer clears all comment text: System allows saving with null Comment__c value | GIVEN customer has feedback record less than 30 days old WHEN customer edits and saves comment THEN Comment__c is updated with new text and Last_Modified_Date__c is updated GIVEN customer has feedback record older than 30 days WHEN customer views record THEN Edit button is disabled and warning message is displayed GIVEN customer edits comment to blank WHEN customer saves THEN Comment__c is set to null and Rating__c remains unchanged | Customer_Feedback__c | Customer_Feedback__c.Comment__c, Customer_Feedback__c.Last_Modified_Date__c, Customer_Feedback__c.Submission_Date__c
UC-003-03 | BR-003 | Support Agent Reviews Customer Feedback Comments | Support Agent | Support agent accesses customer feedback dashboard | 1. Support agent navigates to Customer Feedback list view 2. Support agent filters records by date range and rating value 3. System displays filtered Customer_Feedback__c records with Comment__c visible 4. Support agent clicks on record to view full comment details 5. Support agent marks feedback as Reviewed__c = true 6. System timestamps Review_Date__c field | 3a. If Comment__c is null: System displays 'No comment provided' in list view 5a. If support agent adds internal note: System populates Internal_Notes__c field without modifying Comment__c | GIVEN support agent applies filters WHEN system displays results THEN all records show Rating__c and Comment__c values in list view GIVEN support agent marks feedback as reviewed WHEN save occurs THEN Reviewed__c = true and Review_Date__c = current timestamp GIVEN feedback has null Comment__c WHEN displayed in list view THEN 'No comment provided' text appears GIVEN support agent adds internal note WHEN saved THEN Internal_Notes__c is populated and Comment__c remains unchanged | Customer_Feedback__c | Customer_Feedback__c.Comment__c, Customer_Feedback__c.Rating__c, Customer_Feedback__c.Reviewed__c, Customer_Feedback__c.Review_Date__c, Customer_Feedback__c.Internal_Notes__c
UC-003-04 | BR-003 | System Analyzes Comment Sentiment for Reporting | System | Customer_Feedback__c record is created or Comment__c is updated | 1. System detects new or updated Comment__c value 2. System invokes Einstein Sentiment Analysis API with comment text 3. System receives sentiment score (Positive/Neutral/Negative) 4. System populates Sentiment__c field with analysis result 5. System updates Sentiment_Confidence__c with confidence percentage | 1a. If Comment__c is null or empty: System sets Sentiment__c = 'Not Applicable' and skips API call 2a. If API call fails: System logs error and sets Sentiment__c = 'Analysis Failed' | GIVEN Comment__c contains text WHEN record is saved THEN Sentiment__c is populated with Positive, Neutral, or Negative value GIVEN Comment__c is null WHEN record is saved THEN Sentiment__c = 'Not Applicable' and no API call is made GIVEN sentiment analysis completes WHEN result is received THEN Sentiment_Confidence__c shows percentage value between 0-100 | Customer_Feedback__c | Customer_Feedback__c.Comment__c, Customer_Feedback__c.Sentiment__c, Customer_Feedback__c.Sentiment_Confidence__c
UC-004-01 | BR-004 | Auto-capture submission date on feedback creation | Business User | User saves a new feedback record | 1. User navigates to Feedback object and clicks New 2. User enters required feedback details 3. User clicks Save 4. System auto-populates Feedback__c.Submission_Date__c with current date 5. System saves feedback record 6. System displays success message with submission date | 4a. If Submission_Date__c already has value: System retains original date | GIVEN user creates new feedback WHEN user clicks Save THEN Submission_Date__c equals today's date GIVEN feedback record exists WHEN user edits record THEN Submission_Date__c remains unchanged GIVEN Submission_Date__c is populated WHEN user views record THEN date displays in user's locale format | Feedback__c | Feedback__c.Submission_Date__c
UC-004-02 | BR-004 | Prevent manual modification of submission date | Business User | User attempts to edit Submission_Date__c field | 1. User opens existing feedback record in edit mode 2. System displays Submission_Date__c as read-only field 3. User modifies other feedback fields 4. User clicks Save 5. System saves changes without altering Submission_Date__c | 2a. If System Admin profile: Field remains editable for data correction | GIVEN standard user edits feedback WHEN viewing Submission_Date__c THEN field is read-only GIVEN System Admin edits feedback WHEN viewing Submission_Date__c THEN field is editable GIVEN user saves edited feedback WHEN Submission_Date__c unchanged THEN original date persists | Feedback__c | Feedback__c.Submission_Date__c
UC-004-03 | BR-004 | Generate feedback report by submission date | Business User | User runs feedback report for specific date range | 1. User navigates to Reports tab 2. User selects Feedback by Submission Date report 3. User sets date range filter on Submission_Date__c 4. User clicks Run Report 5. System displays feedback records within date range 6. System groups results by Submission_Date__c | 5a. If no records found: System displays 'No data available' message | GIVEN user filters by date range WHEN report runs THEN only feedback within range displays GIVEN report includes Submission_Date__c WHEN viewing results THEN date column is sortable GIVEN feedback exists WHEN grouping by Submission_Date__c THEN count per date is accurate | Feedback__c | Feedback__c.Submission_Date__c, Feedback__c.Id
UC-004-04 | BR-004 | Validate submission date on data import | System Admin | Admin imports feedback records via Data Loader | 1. Admin prepares CSV with feedback data including Submission_Date__c 2. Admin initiates Data Loader insert operation 3. System validates Submission_Date__c format for each row 4. System inserts records with valid dates 5. System generates error log for invalid date formats | 3a. If Submission_Date__c is blank: System populates with import date 3b. If date format invalid: System skips row and logs error | GIVEN CSV has valid dates WHEN import completes THEN all records inserted with correct Submission_Date__c GIVEN CSV has blank dates WHEN import completes THEN Submission_Date__c equals import date GIVEN CSV has invalid dates WHEN import completes THEN error log identifies failed rows | Feedback__c | Feedback__c.Submission_Date__c
UC-005-01 | BR-005 | Create Feedback Record with Account Association | Customer Service Rep | User clicks New on Feedback object | 1. User clicks New button on Feedback tab 2. System displays Feedback creation form with Account lookup field marked required 3. User searches and selects Account via lookup 4. User enters feedback details (Subject, Description, Rating) 5. User clicks Save 6. System validates Account is populated and saves Feedback record | 3a. If Account not found: User clicks New Account to create account first 6a. If Account field empty: System displays error 'Account is required' and prevents save | GIVEN user is on Feedback creation form WHEN Account field is empty and user clicks Save THEN system displays validation error GIVEN user selects valid Account WHEN user saves Feedback THEN Feedback__c.Account__c is populated with Account ID GIVEN Feedback record exists WHEN user views record THEN Account name displays as clickable link GIVEN Account is deleted WHEN user attempts to delete THEN system prevents deletion if related Feedback records exist | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Rating__c
UC-005-02 | BR-005 | View Account-Level Feedback Summary Report | Account Manager | User navigates to Feedback Reports tab | 1. User opens Feedback by Account report 2. System displays report grouped by Account name 3. User applies filters for date range or feedback rating 4. System refreshes report showing feedback count and average rating per Account 5. User clicks Account name to drill into detailed feedback records | 3a. If no feedback exists for date range: System displays 'No records to display' message | GIVEN Feedback records exist WHEN user runs report THEN each row displays Account name with feedback count GIVEN multiple Feedback records per Account WHEN report loads THEN system calculates average rating per Account GIVEN user filters by date range WHEN report refreshes THEN only Feedback within date range displays GIVEN user clicks Account name in report WHEN drill-through executes THEN related Feedback records display | Account, Feedback__c, Report | Feedback__c.Account__c, Feedback__c.Rating__c, Feedback__c.CreatedDate
UC-005-03 | BR-005 | Display Related Feedback on Account Page | Sales Rep | User opens Account record detail page | 1. User navigates to Account record 2. System displays Account detail page with Related Feedback list 3. User views feedback count and recent feedback entries 4. User clicks View All to see complete feedback history 5. System opens filtered Feedback list view for that Account | 3a. If no feedback exists: System displays 'No feedback records' message in related list | GIVEN Account has related Feedback WHEN user views Account page THEN Related Feedback list displays up to 10 recent records GIVEN user is on Account page WHEN user clicks New in Related Feedback THEN Feedback__c.Account__c auto-populates with current Account ID GIVEN Feedback records exist WHEN user clicks View All THEN system displays all Feedback filtered by Account GIVEN user lacks read access to Feedback WHEN Account page loads THEN Related Feedback section is hidden | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Subject__c, Feedback__c.CreatedDate
UC-005-04 | BR-005 | Bulk Import Feedback with Account Matching | System Administrator | Admin initiates Data Import Wizard for Feedback | 1. Admin prepares CSV with Feedback data including Account External ID 2. Admin opens Data Import Wizard and selects Feedback object 3. Admin maps CSV columns to Feedback fields and Account lookup via External ID 4. System validates all Account External IDs exist 5. System imports Feedback records and associates with matched Accounts 6. System displays import results with success and error counts | 4a. If Account External ID not found: System logs error and skips that row 4b. If Account field blank in CSV: System rejects row with validation error | GIVEN CSV contains valid Account External IDs WHEN import executes THEN Feedback__c.Account__c populates with matching Account ID GIVEN CSV row has blank Account field WHEN import runs THEN system skips row and logs validation error GIVEN 100 rows in CSV with 95 valid Accounts WHEN import completes THEN 95 records created and 5 errors logged GIVEN import completes WHEN admin views results THEN error file lists rows with missing or invalid Account references | Account, Feedback__c | Feedback__c.Account__c, Account.External_ID__c, Feedback__c.Subject__c, Feedback__c.Description__c
UC-006-01 | BR-006 | Calculate Average Rating on Feedback Creation | System | New Feedback record is created and linked to Account | 1. System detects new Feedback__c record inserted with Account lookup populated 2. System queries all Feedback__c records related to the Account 3. System calculates average of Feedback__c.Rating__c field values 4. System updates Account.Average_Rating__c with calculated value 5. System rounds result to two decimal places | 2a. If no Feedback records exist: set Account.Average_Rating__c to null 3a. If Rating__c is null on any record: exclude from calculation | GIVEN Account has 3 Feedback records with ratings 4, 5, 3 WHEN new Feedback is created THEN Account.Average_Rating__c = 4.00 GIVEN Account has no Feedback records WHEN last Feedback is deleted THEN Account.Average_Rating__c = null GIVEN Feedback has null Rating__c WHEN calculating average THEN System excludes null values from calculation GIVEN calculation completes WHEN viewing Account record THEN Average_Rating__c displays within 2 seconds | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-006-02 | BR-006 | Recalculate Average Rating on Feedback Update | System | Existing Feedback record Rating__c field is modified | 1. System detects Feedback__c.Rating__c field value changed 2. System identifies related Account via Feedback__c.Account__c lookup 3. System queries all Feedback__c records for that Account 4. System recalculates average of all Rating__c values 5. System updates Account.Average_Rating__c with new average | 1a. If Rating__c changed from value to null: recalculate excluding null 2a. If Account__c lookup is changed: recalculate for both old and new Account | GIVEN Account has Average_Rating__c = 4.00 WHEN Feedback Rating__c changes from 5 to 2 THEN Account.Average_Rating__c recalculates correctly GIVEN Feedback Rating__c changes WHEN update completes THEN Account.Average_Rating__c reflects new value immediately GIVEN Feedback moved to different Account WHEN Account__c lookup changes THEN both Accounts recalculate Average_Rating__c | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-006-03 | BR-006 | Recalculate Average Rating on Feedback Deletion | System | Feedback record is deleted from Account | 1. System detects Feedback__c record deletion 2. System captures Account__c lookup value before deletion 3. System queries remaining Feedback__c records for Account 4. System recalculates average from remaining Rating__c values 5. System updates Account.Average_Rating__c with new average | 3a. If no Feedback records remain: set Account.Average_Rating__c to null | GIVEN Account has 4 Feedback records with Average_Rating__c = 4.00 WHEN 1 Feedback is deleted THEN Account.Average_Rating__c recalculates from remaining 3 records GIVEN Account has 1 Feedback record WHEN that Feedback is deleted THEN Account.Average_Rating__c = null GIVEN Feedback is deleted WHEN deletion completes THEN Account.Average_Rating__c updates within 3 seconds | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-006-04 | BR-006 | Display Average Rating on Account Page | Business User | User navigates to Account record detail page | 1. User opens Account record 2. System displays Account.Average_Rating__c field on page layout 3. System shows value as read-only number field 4. System displays two decimal places or null if no ratings | 2a. If Average_Rating__c is null: display empty or '--' placeholder | GIVEN Account has Average_Rating__c = 4.25 WHEN User views Account THEN field displays '4.25' as read-only GIVEN Account has no Feedback records WHEN User views Account THEN Average_Rating__c displays as empty GIVEN User has read access to Account WHEN viewing record THEN Average_Rating__c is visible on page layout GIVEN User attempts to edit WHEN clicking Average_Rating__c field THEN System prevents manual editing | Account | Account.Average_Rating__c
UC-007-01 | BR-007 | Recalculate Account Average Rating on New Feedback | System | New Feedback__c record is created | 1. System detects new Feedback__c record creation 2. System retrieves associated Account via Feedback__c.Account__c lookup 3. System queries all related Feedback__c records for the Account 4. System calculates average of Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field 6. System commits transaction | 3a. If no other feedback exists: Set Account.Average_Rating__c to current feedback rating 4a. If Rating__c is null: Exclude from calculation and log error | GIVEN an Account with 2 existing feedbacks rated 4 and 5 WHEN a new feedback with rating 3 is submitted THEN Account.Average_Rating__c = 4.0 GIVEN an Account with no existing feedbacks WHEN first feedback with rating 5 is submitted THEN Account.Average_Rating__c = 5.0 GIVEN a new feedback is created WHEN calculation completes THEN Account.Average_Rating__c is updated within 5 seconds GIVEN a feedback with null Rating__c WHEN submitted THEN Account.Average_Rating__c excludes null value from calculation | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-007-02 | BR-007 | Recalculate Account Average Rating on Feedback Update | System | Existing Feedback__c record Rating__c field is updated | 1. System detects Feedback__c.Rating__c field change 2. System retrieves associated Account via Feedback__c.Account__c 3. System queries all related Feedback__c records for the Account 4. System recalculates average of all Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field | 1a. If Rating__c changed from null to value: Include in calculation 1b. If Rating__c changed from value to null: Exclude from calculation | GIVEN an Account with feedbacks rated 3, 4, 5 WHEN one feedback rating changes from 3 to 5 THEN Account.Average_Rating__c updates to 4.67 GIVEN a feedback rating is updated WHEN recalculation completes THEN Account.Average_Rating__c reflects new average GIVEN Rating__c changes to null WHEN recalculation runs THEN system excludes null rating from average | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-007-03 | BR-007 | Recalculate Account Average Rating on Feedback Deletion | System | Feedback__c record is deleted | 1. System detects Feedback__c record deletion 2. System retrieves associated Account from deleted record 3. System queries remaining Feedback__c records for the Account 4. System recalculates average of remaining Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field | 3a. If no remaining feedback exists: Set Account.Average_Rating__c to null or 0 | GIVEN an Account with feedbacks rated 2, 4, 6 WHEN feedback rated 2 is deleted THEN Account.Average_Rating__c updates to 5.0 GIVEN an Account with one feedback WHEN that feedback is deleted THEN Account.Average_Rating__c is set to null GIVEN a feedback is deleted WHEN recalculation completes THEN Account.Average_Rating__c excludes deleted feedback rating | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-007-04 | BR-007 | Handle Bulk Feedback Submission with Rating Recalculation | System | Multiple Feedback__c records created via data import or API | 1. System detects bulk Feedback__c record creation 2. System groups feedbacks by Account__c lookup field 3. System calculates average rating per Account in batch 4. System updates Account.Average_Rating__c for all affected Accounts 5. System processes within governor limits | 5a. If governor limits approached: Process in smaller batches asynchronously | GIVEN 200 feedbacks imported for 50 Accounts WHEN bulk insert completes THEN all 50 Account.Average_Rating__c fields are updated correctly GIVEN bulk feedback creation WHEN processing THEN system completes within Salesforce governor limits GIVEN multiple feedbacks for same Account WHEN created simultaneously THEN Account.Average_Rating__c reflects all new ratings | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-01 | BR-008 | Recalculate Account Average Rating on Feedback Update | System | Feedback__c.Rating__c field is modified | 1. System detects Rating__c field change on Feedback__c record 2. System queries all Feedback__c records related to parent Account 3. System calculates average of all Rating__c values 4. System updates Account.Average_Rating__c with calculated value 5. System commits transaction | 2a. If no other Feedback records exist: Set Account.Average_Rating__c to current Rating__c value 3a. If Rating__c is null on any record: Exclude from average calculation | GIVEN Account has 3 Feedback records with ratings 3, 4, 5 WHEN one rating changes from 4 to 2 THEN Account.Average_Rating__c updates to 3.33 GIVEN Account has 1 Feedback record with rating 5 WHEN rating changes to 3 THEN Account.Average_Rating__c updates to 3 GIVEN Account has 2 Feedback records with ratings 4 and null WHEN rating 4 changes to 2 THEN Account.Average_Rating__c calculates as 2 GIVEN Feedback rating changes WHEN calculation completes THEN Account.Average_Rating__c updates within same transaction | Account, Feedback__c | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-02 | BR-008 | Handle Bulk Feedback Rating Updates | System | Multiple Feedback__c records updated via Data Loader or API | 1. System detects bulk update of Rating__c on multiple Feedback__c records 2. System identifies unique parent Account IDs from updated records 3. System processes each Account once to recalculate average 4. System updates all affected Account.Average_Rating__c values 5. System completes bulk operation within governor limits | 3a. If updates exceed 200 Accounts: Process in batches to avoid CPU timeout 5a. If SOQL limit approached: Aggregate queries by Account to reduce query count | GIVEN 500 Feedback records updated across 50 Accounts WHEN bulk update executes THEN all 50 Account.Average_Rating__c values recalculate correctly GIVEN bulk update of Feedback records WHEN processing THEN system stays within SOQL query limits (max 100 queries) GIVEN multiple Feedback records for same Account updated WHEN calculation runs THEN Account average recalculates only once per transaction | Account, Feedback__c | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-03 | BR-008 | Validate Rating Value Before Recalculation | System | Feedback__c.Rating__c field value is changed | 1. System validates Rating__c is within acceptable range (1-5) 2. System confirms Account__c lookup field is populated 3. System proceeds with average rating recalculation 4. System updates Account.Average_Rating__c | 1a. If Rating__c is outside range or negative: Prevent save and display error message 2a. If Account__c is null: Skip recalculation and log error | GIVEN Feedback__c.Rating__c is set to 6 WHEN user saves THEN system prevents save with error 'Rating must be between 1 and 5' GIVEN Feedback__c.Rating__c is valid and Account__c is populated WHEN save occurs THEN recalculation executes successfully GIVEN Feedback__c.Account__c is null WHEN Rating__c changes THEN system skips recalculation without error | Feedback__c, Account | Feedback__c.Rating__c, Feedback__c.Account__c, Account.Average_Rating__c
UC-008-04 | BR-008 | Update Average Rating Precision and Rounding | System | Average rating calculation completes | 1. System calculates sum of all Rating__c values for Account 2. System divides sum by count of non-null Rating__c records 3. System rounds result to 2 decimal places 4. System updates Account.Average_Rating__c with rounded value | 2a. If count is zero: Set Account.Average_Rating__c to null | GIVEN Account has ratings 3, 4, 5 WHEN average calculates THEN Account.Average_Rating__c equals 4.00 GIVEN Account has ratings 3, 3, 5 WHEN average calculates THEN Account.Average_Rating__c equals 3.67 GIVEN all Feedback records deleted for Account WHEN recalculation runs THEN Account.Average_Rating__c sets to null | Account, Feedback__c | Feedback__c.Rating__c, Account.Average_Rating__c
UC-009-01 | BR-009 | Recalculate Account Rating on Feedback Deletion | System | Feedback__c record is deleted | 1. User deletes Feedback__c record 2. System captures deleted Feedback__c.Account__c lookup value 3. System queries remaining Feedback__c records for same Account 4. System calculates average of Feedback__c.Rating__c values 5. System updates Account.Average_Rating__c field 6. System commits transaction | 3a. If no remaining Feedback records exist: Set Account.Average_Rating__c to null 4a. If Rating__c is null on any record: Exclude from calculation | GIVEN Account has 3 Feedback records with ratings 4, 5, 3 WHEN user deletes Feedback with rating 5 THEN Account.Average_Rating__c = 3.5 GIVEN Account has 1 Feedback record WHEN user deletes that Feedback THEN Account.Average_Rating__c = null GIVEN Feedback deletion occurs WHEN recalculation completes THEN Account Last Modified Date is updated GIVEN bulk delete of 200 Feedback records WHEN deletion completes THEN all associated Accounts have updated Average_Rating__c | Account, Feedback__c | Account.Average_Rating__c, Feedback__c.Account__c, Feedback__c.Rating__c
UC-009-02 | BR-009 | Handle Feedback Deletion Without Account Association | System | Feedback__c record without Account lookup is deleted | 1. User deletes Feedback__c record 2. System checks Feedback__c.Account__c field 3. System identifies Account__c is null 4. System completes deletion without recalculation 5. System logs deletion event | 2a. If Account__c was populated but Account is deleted: Skip recalculation | GIVEN Feedback__c.Account__c is null WHEN user deletes Feedback THEN no Account record is updated GIVEN Feedback references deleted Account WHEN user deletes Feedback THEN deletion succeeds without error | Feedback__c, Account | Feedback__c.Account__c
UC-009-03 | BR-009 | Recalculate Multiple Accounts on Bulk Deletion | System | Multiple Feedback__c records deleted in bulk operation | 1. User selects and deletes multiple Feedback__c records 2. System collects unique Account__c IDs from deleted records 3. System queries remaining Feedback__c for each Account 4. System calculates average Rating__c per Account 5. System performs bulk update on Account.Average_Rating__c 6. System completes transaction within governor limits | 6a. If governor limits approached: Process Accounts in batches using Queueable Apex | GIVEN 50 Feedback records across 10 Accounts deleted WHEN bulk delete executes THEN all 10 Accounts have recalculated Average_Rating__c GIVEN bulk deletion WHEN processing completes THEN operation stays within SOQL query limits (100 queries) GIVEN bulk deletion WHEN processing completes THEN operation stays within DML row limits (10,000 rows) | Feedback__c, Account | Feedback__c.Account__c, Feedback__c.Rating__c, Account.Average_Rating__c
UC-010-01 | BR-010 | Submit New Customer Feedback from Account Page | Business User | User clicks 'New Feedback' button on Account page | 1. User clicks 'New Feedback' button on Account record page 2. System displays embedded feedback form component 3. User enters feedback details (Type, Category, Comments, Priority) 4. User clicks 'Submit' button 5. System validates required fields are populated 6. System creates Customer_Feedback__c record linked to Account | 5a. If required fields missing: System displays inline error messages, prevents submission 6a. If submission fails: System displays error toast notification with retry option | GIVEN user is on Account page WHEN user clicks 'New Feedback' button THEN feedback form displays without page navigation GIVEN user completes all required fields WHEN user clicks Submit THEN Customer_Feedback__c record is created with Account__c lookup populated GIVEN user submits form with missing required fields WHEN validation runs THEN inline error messages display and submission is blocked GIVEN feedback is successfully submitted WHEN record is created THEN success toast notification displays and form clears | Account, Customer_Feedback__c | Customer_Feedback__c.Account__c, Customer_Feedback__c.Feedback_Type__c, Customer_Feedback__c.Category__c, Customer_Feedback__c.Comments__c, Customer_Feedback__c.Priority__c
UC-010-02 | BR-010 | Cancel Feedback Submission and Clear Form | Business User | User clicks 'Cancel' button on feedback form | 1. User begins entering feedback data in form 2. User clicks 'Cancel' button 3. System displays confirmation modal if data entered 4. User confirms cancellation 5. System clears all form fields and closes form | 3a. If no data entered: System immediately clears form without confirmation 4a. If user clicks 'Go Back' on modal: System returns to form with data intact | GIVEN user has entered data in form WHEN user clicks Cancel THEN confirmation modal displays GIVEN user confirms cancellation WHEN modal action completes THEN all form fields are cleared GIVEN user has not entered data WHEN user clicks Cancel THEN form clears immediately without confirmation | Customer_Feedback__c
UC-010-03 | BR-010 | Auto-populate Account Context in Feedback Form | System | Feedback form component loads on Account page | 1. User opens feedback form from Account record page 2. System retrieves current Account record ID from page context 3. System pre-populates Account__c lookup field with current Account 4. System displays Account Name as read-only reference 5. System disables Account__c field to prevent modification | 2a. If Account ID cannot be retrieved: System displays error message and disables form submission | GIVEN user opens form from Account page WHEN form loads THEN Account__c field is pre-populated with current Account ID GIVEN Account__c field is populated WHEN form displays THEN Account Name shows as read-only text GIVEN form is loaded WHEN user attempts to change Account THEN Account__c field is disabled and cannot be modified | Account, Customer_Feedback__c | Customer_Feedback__c.Account__c, Account.Name
UC-010-04 | BR-010 | View Feedback Confirmation and Record Details | Business User | Customer_Feedback__c record is successfully created | 1. System creates Customer_Feedback__c record 2. System displays success toast with feedback record number 3. System provides 'View Record' link in toast notification 4. User clicks 'View Record' link 5. System navigates to Customer_Feedback__c record detail page in new subtab | 3a. If user dismisses toast: Form clears and remains on Account page without navigation | GIVEN feedback record is created WHEN creation completes THEN success toast displays with record number GIVEN success toast displays WHEN user clicks 'View Record' THEN Customer_Feedback__c detail page opens in new subtab GIVEN success toast displays WHEN user dismisses toast THEN user remains on Account page with cleared form | Customer_Feedback__c, Account | Customer_Feedback__c.Name
UC-011-01 | BR-011 | Submit Feedback with Star Rating Selection | Business User | User opens feedback submission form | 1. User opens feedback submission form 2. System displays rating selector with 1-5 star options 3. User clicks on desired star rating (1-5) 4. System highlights selected rating and all stars up to selection 5. User completes remaining form fields 6. User clicks Submit button 7. System saves Feedback__c record with Rating__c field value | 3a. If user clicks different star rating: System updates selection and highlights new rating 6a. If no rating selected: System displays error 'Rating is required' and prevents submission | GIVEN user is on feedback form WHEN form loads THEN rating selector displays 5 clickable stars GIVEN user clicks 3-star rating WHEN selection is made THEN stars 1-3 are highlighted and Rating__c = 3 GIVEN user has not selected rating WHEN user clicks Submit THEN error message displays and form does not submit GIVEN user selects 5-star rating WHEN form is submitted THEN Feedback__c.Rating__c = 5 | Feedback__c | Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Submitted_Date__c
UC-011-02 | BR-011 | Change Star Rating Before Submission | Business User | User selects initial star rating then changes mind | 1. User selects initial star rating (e.g., 2 stars) 2. System highlights stars 1-2 3. User clicks different star rating (e.g., 4 stars) 4. System updates highlight to stars 1-4 5. User submits form 6. System saves Feedback__c with final Rating__c value | 3a. If user hovers over different star: System shows preview highlight without committing selection | GIVEN user selected 2-star rating WHEN user clicks 4-star rating THEN highlight updates to 4 stars and Rating__c = 4 GIVEN user changes rating multiple times WHEN form is submitted THEN only final rating value is saved GIVEN user hovers over star WHEN mouse moves away without clicking THEN previous selection remains unchanged | Feedback__c | Feedback__c.Rating__c
UC-011-03 | BR-011 | Display Visual Star Rating Indicator | Business User | User views feedback submission form | 1. User navigates to feedback form 2. System renders rating selector component 3. System displays 5 empty star icons in horizontal row 4. System shows label 'Select Rating (1-5 stars)' above selector 5. User hovers over star icon 6. System displays hover state with visual feedback | 5a. If user is on mobile device: System displays touch-optimized star icons with larger tap targets | GIVEN user views form WHEN page loads THEN 5 empty star icons display horizontally with equal spacing GIVEN user hovers over 3rd star WHEN mouse enters star area THEN stars 1-3 show hover state GIVEN user is on mobile WHEN form loads THEN star icons are minimum 44x44 pixels for touch accessibility GIVEN rating selector displays WHEN user views it THEN descriptive label is visible above stars | Feedback__c | Feedback__c.Rating__c
UC-012-01 | BR-012 | Submit Customer Feedback with Comments | Business User | User navigates to feedback submission form | 1. User opens feedback submission form 2. System displays form with text area for comments 3. User enters customer comments in text area 4. User clicks Submit button 5. System validates comment field is not empty 6. System creates Feedback__c record with comments | 5a. If comment field is empty: System displays error message 'Customer comments are required' 5b. If comment exceeds character limit: System displays error message 'Comments cannot exceed 32,000 characters' | GIVEN user is on feedback form WHEN form loads THEN text area for comments is visible and enabled GIVEN user enters valid comments WHEN user clicks Submit THEN Feedback__c record is created with Comments__c field populated GIVEN user submits empty comment WHEN user clicks Submit THEN error message displays and record is not created GIVEN user enters 32,000 characters WHEN user clicks Submit THEN record saves successfully | Feedback__c | Feedback__c.Comments__c, Feedback__c.Submitted_Date__c, Feedback__c.Submitted_By__c
UC-012-02 | BR-012 | Edit Customer Comments Before Submission | Business User | User enters text in comments text area | 1. User types customer comments in text area 2. System displays character count below text area 3. User edits or deletes text content 4. System updates character count in real-time 5. User completes editing and clicks Submit | 4a. If character count exceeds limit: System disables Submit button and highlights text area in red | GIVEN user types in text area WHEN each character is entered THEN character count updates immediately GIVEN user exceeds character limit WHEN typing continues THEN Submit button is disabled GIVEN user pastes text WHEN text is pasted THEN character count reflects total characters including pasted content | Feedback__c | Feedback__c.Comments__c
UC-012-03 | BR-012 | View Required Field Indicator for Comments | Business User | User opens feedback submission form | 1. User navigates to feedback form 2. System displays text area with red asterisk indicator 3. System displays label 'Customer Comments *' 4. User attempts to submit without entering comments 5. System displays validation error message | 4a. If user enters comments then deletes all text: System shows inline error 'This field is required' | GIVEN form loads WHEN user views comments field THEN red asterisk is visible next to field label GIVEN user submits empty form WHEN Submit is clicked THEN error message appears on comments field GIVEN user enters then clears comments WHEN field loses focus THEN inline validation error displays | Feedback__c | Feedback__c.Comments__c
UC-012-04 | BR-012 | Preserve Comments on Form Validation Error | Business User | User submits form with validation errors | 1. User enters customer comments in text area 2. User fills other required fields incorrectly 3. User clicks Submit button 4. System validates all fields and finds errors 5. System displays error messages and retains entered comments 6. User corrects errors and resubmits successfully | 5a. If session times out: System redirects to login and comments are lost | GIVEN user enters comments WHEN form validation fails THEN comments text remains in text area GIVEN validation errors occur WHEN user corrects errors THEN previously entered comments are still present GIVEN user enters comments WHEN page refreshes due to error THEN comments are preserved | Feedback__c | Feedback__c.Comments__c
UC-013-01 | BR-013 | Submit Feedback from Account Page with Auto-Link | Business User | User clicks Submit Feedback button on Account page | 1. User navigates to Account detail page 2. User clicks Submit Feedback button 3. System opens feedback submission modal with Account ID pre-populated 4. User enters feedback text and selects feedback type 5. User clicks Submit 6. System creates Feedback__c record with Account__c field populated | 4a. If feedback text is empty: System displays error message 'Feedback text is required' 6a. If Account ID is missing: System logs error and prevents submission | GIVEN user is on Account detail page WHEN user submits feedback THEN Feedback__c.Account__c equals current Account.Id GIVEN user submits feedback WHEN Feedback__c is created THEN user sees success message with feedback reference number GIVEN user leaves feedback text empty WHEN user clicks Submit THEN system displays validation error GIVEN feedback is submitted WHEN user views Account related list THEN new feedback appears in Account Feedback related list | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Feedback_Text__c, Feedback__c.Feedback_Type__c, Account.Id
UC-013-02 | BR-013 | Validate Account Context Before Feedback Submission | System | User attempts to submit feedback from Account page | 1. User clicks Submit on feedback form 2. System retrieves current Account.Id from page context 3. System validates Account record exists and is accessible 4. System validates user has read access to Account 5. System proceeds with feedback creation | 3a. If Account record does not exist: System displays error 'Account not found' and prevents submission 4a. If user lacks Account access: System displays error 'Insufficient privileges' and prevents submission | GIVEN Account is deleted WHEN user submits feedback THEN system prevents submission with error message GIVEN user lacks Account read access WHEN user attempts feedback submission THEN system displays insufficient privileges error GIVEN valid Account context WHEN system validates THEN feedback submission proceeds | Account, Feedback__c | Account.Id, Feedback__c.Account__c
UC-013-03 | BR-013 | Display Account Information in Feedback Form | Business User | User opens feedback submission form from Account page | 1. User clicks Submit Feedback button on Account page 2. System retrieves Account.Name and Account.AccountNumber 3. System displays feedback form with Account details in header 4. System disables Account lookup field to prevent manual changes 5. User views Account context while entering feedback | 2a. If Account data cannot be retrieved: System displays generic feedback form without Account context | GIVEN user opens feedback form from Account WHEN form loads THEN Account.Name displays in form header GIVEN feedback form is open WHEN user views Account lookup field THEN field is disabled and pre-populated GIVEN user submits feedback WHEN viewing confirmation THEN Account name appears in success message | Account, Feedback__c | Account.Name, Account.AccountNumber, Feedback__c.Account__c
UC-013-04 | BR-013 | Prevent Feedback Submission Without Account Context | System | User attempts to access feedback form outside Account page | 1. User navigates to Feedback__c object tab or home page 2. User clicks New Feedback button 3. System detects no Account context in URL parameters 4. System displays standard feedback form with Account lookup enabled 5. User manually selects Account from lookup field | 3a. If accessed from Account page: System auto-populates and locks Account__c field | GIVEN user creates feedback from Feedback tab WHEN form loads THEN Account lookup field is enabled and empty GIVEN user creates feedback from Account page WHEN form loads THEN Account lookup field is disabled and populated GIVEN no Account context exists WHEN user submits without selecting Account THEN system displays validation error | Feedback__c, Account | Feedback__c.Account__c
UC-014-01 | BR-014 | Display Success Message After Feedback Submission | Business User | User clicks Submit button on feedback form | 1. User completes feedback form fields 2. User clicks Submit button 3. System validates required fields are populated 4. System creates Feedback__c record 5. System displays success confirmation message 6. System clears form fields | 3a. If required fields missing: System displays field-level error messages and prevents submission 4a. If record creation fails: System displays error message with retry option | GIVEN user has completed all required fields WHEN user clicks Submit THEN success message displays within 2 seconds GIVEN feedback record is created WHEN submission completes THEN message includes confirmation text 'Your feedback has been successfully submitted' GIVEN success message displays WHEN user views screen THEN form fields are cleared and ready for new entry GIVEN submission fails WHEN error occurs THEN error message displays with specific failure reason | Feedback__c | Feedback__c.Status__c, Feedback__c.Submitted_Date__c, Feedback__c.Submitter__c
UC-014-02 | BR-014 | Send Email Confirmation After Feedback Submission | Business User | Feedback__c record is created with Status__c = 'Submitted' | 1. System creates Feedback__c record 2. System sets Feedback__c.Status__c to 'Submitted' 3. System retrieves submitter email from User record 4. System sends confirmation email to submitter 5. System updates Feedback__c.Confirmation_Sent__c to TRUE | 3a. If submitter email is blank: System logs error and skips email send 4a. If email send fails: System retries once after 5 minutes | GIVEN feedback record is created WHEN Status__c = 'Submitted' THEN confirmation email is sent within 1 minute GIVEN email is sent successfully WHEN process completes THEN Feedback__c.Confirmation_Sent__c = TRUE GIVEN email contains feedback details WHEN user receives email THEN email includes Feedback ID and submission timestamp GIVEN email send fails WHEN retry limit reached THEN system creates Task for admin review | Feedback__c, User, Task | Feedback__c.Status__c, Feedback__c.Confirmation_Sent__c, Feedback__c.Submitter__c, User.Email
UC-014-03 | BR-014 | Display Confirmation Banner with Record Details | Business User | Feedback__c record save completes successfully | 1. System saves Feedback__c record 2. System generates unique Feedback ID 3. System displays green success banner at top of page 4. Banner shows confirmation message with Feedback ID and timestamp 5. Banner auto-dismisses after 5 seconds | 5a. If user clicks X icon: Banner dismisses immediately | GIVEN record saves successfully WHEN page refreshes THEN green banner appears at top with success icon GIVEN banner displays WHEN user views message THEN text includes 'Feedback [ID] submitted successfully at [timestamp]' GIVEN banner appears WHEN 5 seconds elapse THEN banner fades out automatically GIVEN banner is visible WHEN user clicks dismiss icon THEN banner closes immediately | Feedback__c | Feedback__c.Name, Feedback__c.CreatedDate
UC-015-01 | BR-015 | Submit Feedback Form with All Required Fields | Business User | User clicks Submit button on feedback form | 1. User fills out feedback form fields 2. User clicks Submit button 3. System validates all required fields are populated 4. System saves feedback record to Feedback__c object 5. System displays success confirmation message 6. System clears form for new entry | 3a. If any required field is empty: System displays inline error message and prevents submission | GIVEN all required fields are completed WHEN user clicks Submit THEN feedback record is created successfully GIVEN all required fields are completed WHEN user clicks Submit THEN success message displays GIVEN required fields are completed WHEN submission succeeds THEN form clears to blank state | Feedback__c | Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Category__c, Feedback__c.Submitted_Date__c
UC-015-02 | BR-015 | Prevent Submission with Missing Required Fields | Business User | User clicks Submit button with incomplete required fields | 1. User partially fills out feedback form 2. User clicks Submit button 3. System validates required fields 4. System identifies empty required fields 5. System displays error message listing missing fields 6. System keeps form data intact for user correction | 5a. If only one field missing: System highlights specific field with red border and inline error text 5b. If multiple fields missing: System displays summary error at top and highlights all missing fields | GIVEN required field is empty WHEN user clicks Submit THEN submission is blocked and error displays GIVEN multiple required fields empty WHEN user clicks Submit THEN all missing fields are highlighted GIVEN validation fails WHEN error displays THEN existing form data is preserved GIVEN error displayed WHEN user fills missing field THEN error message clears dynamically | Feedback__c | Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Category__c
UC-015-03 | BR-015 | Display Real-Time Required Field Indicators | Business User | User opens feedback form | 1. User navigates to feedback form page 2. System loads form with all fields 3. System displays red asterisk next to required field labels 4. System shows helper text indicating required fields must be completed | 4a. If user focuses on required field then leaves it blank: System displays inline validation error immediately | GIVEN form loads WHEN user views form THEN all required fields show red asterisk indicator GIVEN user focuses on required field WHEN user leaves field blank THEN inline error appears immediately GIVEN required field has value WHEN user moves to next field THEN no error displays | Feedback__c | Feedback__c.Subject__c, Feedback__c.Description__c, Feedback__c.Category__c
UC-015-04 | BR-015 | Validate Field Format for Required Fields | Business User | User enters data in required field with format requirements | 1. User enters data in required field with specific format 2. User moves focus away from field or clicks Submit 3. System validates field is not empty 4. System validates data format matches requirements 5. System allows progression if both validations pass | 4a. If format invalid: System displays format error message with example of correct format 4b. If field empty: System displays required field error message | GIVEN required email field WHEN user enters invalid email format THEN format error displays and submission blocked GIVEN required phone field WHEN user enters non-numeric characters THEN format error displays GIVEN required field with valid format WHEN user clicks Submit THEN validation passes GIVEN format error displayed WHEN user corrects format THEN error clears and field shows valid state | Feedback__c | Feedback__c.Email__c, Feedback__c.Phone__c, Feedback__c.Subject__c
UC-016-01 | BR-016 | Prepare External Feedback Data for Migration | System Administrator | Admin receives 50 historical feedback records from external source | 1. Admin downloads feedback data from external source 2. Admin validates data format matches Salesforce import template 3. Admin maps external fields to Feedback__c object fields 4. Admin cleanses data (removes duplicates, formats dates) 5. Admin saves prepared CSV file for import | 2a. If data format invalid: Admin transforms data using Excel/data tool 4a. If duplicates found: Admin flags records for review before import | GIVEN external feedback file WHEN Admin validates format THEN all required fields are present GIVEN 50 records WHEN Admin checks for duplicates THEN duplicate records are identified GIVEN mapped data WHEN Admin reviews CSV THEN all fields match Feedback__c API names | Feedback__c | Feedback__c.External_ID__c, Feedback__c.Feedback_Date__c, Feedback__c.Feedback_Text__c, Feedback__c.Source__c
UC-016-02 | BR-016 | Import Historical Feedback Records via Data Loader | System Administrator | Admin initiates Data Loader import process | 1. Admin opens Salesforce Data Loader and logs in 2. Admin selects Insert operation for Feedback__c object 3. Admin uploads prepared CSV file with 50 records 4. Admin maps CSV columns to Feedback__c fields 5. System validates and imports all records 6. System generates success/error log file | 5a. If validation errors occur: System logs errors and skips failed records 5b. If duplicate External_ID__c detected: System prevents duplicate insert | GIVEN 50 valid records WHEN import completes THEN all 50 Feedback__c records are created GIVEN import process WHEN errors occur THEN error log identifies specific failed records GIVEN duplicate External_ID__c WHEN import runs THEN system prevents duplicate creation GIVEN successful import WHEN Admin queries Feedback__c THEN Source__c = 'Historical Migration' | Feedback__c | Feedback__c.External_ID__c, Feedback__c.Feedback_Date__c, Feedback__c.Feedback_Text__c, Feedback__c.Source__c, Feedback__c.Migrated_Date__c
UC-016-03 | BR-016 | Validate Migrated Feedback Data Integrity | System Administrator | Admin completes feedback data import | 1. Admin runs report on Feedback__c with filter Source__c = 'Historical Migration' 2. System displays count of migrated records 3. Admin verifies record count matches expected 50 records 4. Admin spot-checks 10 random records for data accuracy 5. Admin marks migration as complete in tracking document | 3a. If count mismatch: Admin reviews error log and re-imports failed records 4a. If data inaccuracies found: Admin updates records manually or re-imports | GIVEN migration complete WHEN Admin runs report THEN exactly 50 Feedback__c records exist with Source__c = 'Historical Migration' GIVEN spot-check WHEN Admin reviews 10 records THEN all field values match source data GIVEN validation complete WHEN Admin checks dates THEN all Feedback_Date__c values are valid historical dates | Feedback__c | Feedback__c.Source__c, Feedback__c.Feedback_Date__c, Feedback__c.External_ID__c, Feedback__c.Migrated_Date__c
UC-016-04 | BR-016 | Auto-Stamp Migration Metadata on Import | System | Feedback__c record created with Source__c = 'Historical Migration' | 1. System detects new Feedback__c record creation 2. System checks if Source__c = 'Historical Migration' 3. System populates Migrated_Date__c with today's date 4. System sets Is_Migrated__c = TRUE 5. System saves record with migration metadata | 2a. If Source__c is not 'Historical Migration': System skips migration metadata update | GIVEN new Feedback__c with Source__c = 'Historical Migration' WHEN record created THEN Migrated_Date__c = TODAY() GIVEN new Feedback__c with Source__c = 'Historical Migration' WHEN record created THEN Is_Migrated__c = TRUE GIVEN new Feedback__c with different Source__c WHEN record created THEN migration fields remain blank | Feedback__c | Feedback__c.Source__c, Feedback__c.Migrated_Date__c, Feedback__c.Is_Migrated__c
UC-017-01 | BR-017 | Download Standardized CSV Template for Feedback Import | System Administrator | Administrator navigates to feedback import configuration page | 1. Administrator clicks 'Download Template' button 2. System generates CSV template with predefined headers 3. System includes all required field mappings in header row 4. System downloads template file to administrator's device 5. Administrator opens template to verify structure | 2a. If template generation fails: display error message with retry option | GIVEN administrator is on import page WHEN clicks Download Template THEN CSV file downloads with correct headers GIVEN template is downloaded WHEN opened in Excel THEN all required feedback fields are present as column headers GIVEN template headers WHEN compared to Feedback__c object THEN all API field names match exactly GIVEN template file WHEN inspected THEN includes sample row with data format examples | Feedback__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Category__c
UC-017-02 | BR-017 | Validate CSV File Against Template Structure | System Administrator | Administrator uploads CSV file for feedback import | 1. Administrator selects CSV file and clicks Upload 2. System reads CSV file headers 3. System compares headers against template specification 4. System validates data types in each column 5. System displays validation summary with pass/fail status 6. System enables Import button if validation passes | 3a. If headers missing or incorrect: display specific missing/incorrect field names 4a. If data type mismatch found: highlight rows and columns with errors 5a. If validation fails: provide downloadable error report with line numbers | GIVEN CSV with correct headers WHEN uploaded THEN validation passes and Import button enables GIVEN CSV with missing required field WHEN uploaded THEN validation fails with specific field name in error message GIVEN CSV with invalid date format WHEN uploaded THEN system identifies exact row and column with error GIVEN validation errors exist WHEN administrator views results THEN error report shows line numbers and error descriptions | Feedback__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Category__c
UC-017-03 | BR-017 | Import Historical Feedback from Validated CSV | System Administrator | Administrator clicks Import button after successful validation | 1. Administrator clicks Import button 2. System maps CSV columns to Feedback__c fields 3. System creates Feedback__c records in batches 4. System tracks import progress with record count 5. System displays completion summary with success/failure counts 6. System sends email notification with import results | 3a. If record creation fails: log error and continue with remaining records 3b. If duplicate detected based on external ID: skip record and log warning 5a. If partial failure occurs: provide downloadable report of failed records | GIVEN validated CSV with 100 rows WHEN import executes THEN 100 Feedback__c records created successfully GIVEN import completes WHEN administrator views summary THEN total processed, success, and failure counts display accurately GIVEN import has failures WHEN administrator downloads error report THEN failed rows with error reasons are listed GIVEN import completes WHEN administrator checks email THEN notification contains import statistics and timestamp | Feedback__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Feedback__c.Category__c, Feedback__c.External_ID__c, Feedback__c.Import_Batch_ID__c
UC-017-04 | BR-017 | Map Custom CSV Fields to Feedback Object | System Administrator | Administrator needs to import feedback with non-standard field names | 1. Administrator uploads CSV with custom headers 2. System displays field mapping interface 3. Administrator maps each CSV column to Feedback__c field 4. Administrator saves custom mapping configuration 5. System validates mapping completeness 6. System applies mapping to proceed with import | 5a. If required fields unmapped: display error and highlight missing mappings 4a. If administrator wants to reuse mapping: save as named template for future imports | GIVEN CSV with custom headers WHEN mapping interface opens THEN all CSV columns display with dropdown of Feedback__c fields GIVEN administrator maps all required fields WHEN saves configuration THEN mapping validation passes GIVEN required field unmapped WHEN administrator attempts to proceed THEN error message identifies unmapped required field GIVEN custom mapping saved WHEN administrator imports next file THEN saved mapping available for selection | Feedback__c, Field_Mapping_Template__c | Feedback__c.Feedback_Date__c, Feedback__c.Customer_Name__c, Feedback__c.Rating__c, Feedback__c.Comments__c, Field_Mapping_Template__c.Name, Field_Mapping_Template__c.Mapping_JSON__c
UC-018-01 | BR-018 | Validate Required Fields During Feedback Import | Data Migration Admin | Admin initiates feedback data import via Data Loader | 1. Admin uploads CSV file containing feedback records 2. System validates all required fields are populated 3. System checks field data types match schema 4. System validates picklist values against defined values 5. System creates Feedback__c records for valid rows 6. System generates import summary report | 2a. If required field missing: reject row and log error with row number 3a. If data type mismatch: reject row and specify expected format 4a. If invalid picklist value: reject row and list valid options | GIVEN feedback import file WHEN required field is blank THEN row is rejected with specific error message GIVEN feedback import file WHEN all required fields populated THEN record is created successfully GIVEN feedback import file WHEN picklist value not in defined list THEN row is rejected with valid values displayed GIVEN import completion WHEN errors exist THEN error log CSV is generated with row numbers and reasons | Feedback__c | Feedback__c.Customer_Name__c, Feedback__c.Feedback_Date__c, Feedback__c.Category__c, Feedback__c.Rating__c, Feedback__c.Comments__c
UC-018-02 | BR-018 | Validate Business Rules for Feedback Ratings | Data Migration Admin | Feedback record insert during migration | 1. System receives Feedback__c record for insert 2. System validates Rating__c is between 1 and 5 3. System validates Feedback_Date__c is not future date 4. System validates Comments__c length does not exceed 32000 characters 5. System inserts record if all validations pass | 2a. If Rating__c outside 1-5 range: reject with valid range message 3a. If Feedback_Date__c is future date: reject with date constraint error 4a. If Comments__c exceeds limit: truncate or reject based on configuration | GIVEN Rating__c value of 0 or 6 WHEN record inserted THEN validation error prevents insert GIVEN Feedback_Date__c in future WHEN record inserted THEN error message displays date must be today or earlier GIVEN Comments__c with 32001 characters WHEN record inserted THEN validation error prevents insert GIVEN all business rules satisfied WHEN record inserted THEN Feedback__c record created successfully | Feedback__c | Feedback__c.Rating__c, Feedback__c.Feedback_Date__c, Feedback__c.Comments__c
UC-018-03 | BR-018 | Validate Feedback Relationship to Account Records | Data Migration Admin | Feedback record with Account lookup during import | 1. System receives Feedback__c record with Account_ID__c value 2. System queries Account object for matching record 3. System validates Account exists and is active 4. System populates Feedback__c.Account__c lookup field 5. System inserts Feedback__c record with valid relationship | 2a. If Account_ID__c not found: reject row and log missing Account ID 3a. If Account is inactive: reject row and specify Account must be active 1a. If Account_ID__c is blank and Account required: reject row with missing relationship error | GIVEN Account_ID__c matches existing Account WHEN Feedback imported THEN Feedback__c.Account__c lookup is populated GIVEN Account_ID__c does not exist WHEN Feedback imported THEN record rejected with Account not found error GIVEN Account.IsActive__c is false WHEN Feedback imported THEN record rejected with inactive Account error GIVEN valid Account relationship WHEN import completes THEN Feedback visible on Account related list | Feedback__c, Account | Feedback__c.Account__c, Feedback__c.Account_ID__c, Account.Id, Account.IsActive__c
UC-018-04 | BR-018 | Validate Duplicate Feedback Prevention Rules | Data Migration Admin | Feedback record insert with potential duplicate | 1. System receives Feedback__c record for insert 2. System checks for existing records with same Account__c and Feedback_Date__c 3. System compares Customer_Email__c if provided 4. System allows insert if no duplicate found 5. System logs successful unique record creation | 2a. If duplicate found based on Account and Date: reject with duplicate error message 3a. If Customer_Email__c matches existing record: flag as potential duplicate and require admin review 2b. If duplicate detection rule configured as warning only: allow insert and create duplicate alert | GIVEN Feedback with same Account__c and Feedback_Date__c exists WHEN new record imported THEN duplicate error prevents insert GIVEN Feedback with same Customer_Email__c exists WHEN new record imported THEN admin receives duplicate alert GIVEN unique Feedback record WHEN imported THEN record created without duplicate warnings GIVEN duplicate detection WHEN error occurs THEN error log includes existing record ID for reference | Feedback__c | Feedback__c.Account__c, Feedback__c.Feedback_Date__c, Feedback__c.Customer_Email__c
UC-018-05 | BR-018 | Generate Data Quality Report Post-Import | Data Migration Admin | Feedback import batch completion | 1. System completes feedback import batch processing 2. System calculates total records processed, successful, and failed 3. System categorizes errors by validation type 4. System generates Data_Quality_Report__c record with metrics 5. System sends email notification to admin with report link | 2a. If zero records processed: send alert for empty import file 4a. If error rate exceeds 10%: flag report as requiring immediate review | GIVEN import batch completes WHEN processing finishes THEN Data_Quality_Report__c record created with accurate counts GIVEN validation errors occurred WHEN report generated THEN errors grouped by type with counts GIVEN import completion WHEN report ready THEN admin receives email with downloadable error log GIVEN error rate above 10% WHEN report generated THEN Report_Status__c set to 'Requires Review' | Data_Quality_Report__c, Feedback__c | Data_Quality_Report__c.Total_Records__c, Data_Quality_Report__c.Successful_Records__c, Data_Quality_Report__c.Failed_Records__c, Data_Quality_Report__c.Error_Rate__c, Data_Quality_Report__c.Report_Status__c
UC-019-01 | BR-019 | Recalculate Account Ratings After Feedback Migration | System Administrator | Feedback data migration batch job completes successfully | 1. System identifies all Accounts linked to migrated Feedback__c records 2. System retrieves all Feedback__c records per Account including newly migrated data 3. System calculates average rating from Feedback__c.Rating__c field 4. System updates Account.Average_Rating__c with calculated value 5. System logs recalculation timestamp in Account.Rating_Last_Calculated__c 6. System sends completion notification to administrator | 3a. If no Feedback__c records exist: Set Account.Average_Rating__c to null 4a. If Account update fails: Log error and continue with next Account 6a. If recalculation affects >1000 Accounts: Send summary report via email | GIVEN historical Feedback__c records are migrated WHEN recalculation runs THEN Account.Average_Rating__c reflects all feedback including migrated data GIVEN Account has 3 existing and 2 migrated Feedback__c records WHEN recalculation completes THEN Account.Average_Rating__c equals average of all 5 ratings GIVEN migration imports 500 Feedback__c records WHEN recalculation completes THEN all affected Accounts show updated Account.Rating_Last_Calculated__c timestamp GIVEN recalculation fails for specific Account WHEN error occurs THEN error is logged and process continues for remaining Accounts | Account, Feedback__c | Account.Average_Rating__c, Account.Rating_Last_Calculated__c, Feedback__c.Rating__c, Feedback__c.Account__c
UC-019-02 | BR-019 | Validate Feedback Data Before Recalculation | Data Migration Specialist | User initiates pre-recalculation validation check | 1. User clicks 'Validate Migrated Data' button on custom migration dashboard 2. System validates Feedback__c.Rating__c values are between 1-5 3. System checks all Feedback__c.Account__c lookups reference valid Accounts 4. System generates validation report showing errors and warnings 5. System displays report on dashboard with pass/fail status | 2a. If invalid ratings found: Flag records in validation report 3a. If orphaned Feedback__c records found: List in report for manual review 5a. If validation fails: Prevent recalculation process from starting | GIVEN migrated Feedback__c has Rating__c = 7 WHEN validation runs THEN record is flagged as invalid in report GIVEN Feedback__c.Account__c references deleted Account WHEN validation runs THEN record is listed as orphaned GIVEN validation finds errors WHEN validation completes THEN recalculation button remains disabled GIVEN all validations pass WHEN validation completes THEN recalculation button becomes enabled | Feedback__c, Account, Migration_Validation_Log__c | Feedback__c.Rating__c, Feedback__c.Account__c, Migration_Validation_Log__c.Status__c, Migration_Validation_Log__c.Error_Details__c
UC-019-03 | BR-019 | Monitor Recalculation Progress in Real-Time | System Administrator | Recalculation batch job starts execution | 1. System creates Recalculation_Job__c record with status 'In Progress' 2. System updates Recalculation_Job__c.Accounts_Processed__c after each batch 3. System updates Recalculation_Job__c.Errors_Encountered__c when failures occur 4. User refreshes custom monitoring dashboard to view progress 5. System updates Recalculation_Job__c.Status__c to 'Completed' when finished | 3a. If error count exceeds threshold: System pauses job and alerts administrator 5a. If job fails: System sets Status__c to 'Failed' and logs error details | GIVEN recalculation processes 100 Accounts WHEN user views dashboard THEN Recalculation_Job__c.Accounts_Processed__c shows 100 GIVEN 5 Account updates fail WHEN batch continues THEN Recalculation_Job__c.Errors_Encountered__c equals 5 GIVEN job completes successfully WHEN final batch finishes THEN Recalculation_Job__c.Status__c = 'Completed' GIVEN error count reaches 50 WHEN threshold exceeded THEN job pauses and admin receives email alert | Recalculation_Job__c, Account | Recalculation_Job__c.Status__c, Recalculation_Job__c.Accounts_Processed__c, Recalculation_Job__c.Errors_Encountered__c, Recalculation_Job__c.Started_Date__c, Recalculation_Job__c.Completed_Date__c
UC-019-04 | BR-019 | Handle Accounts with No Feedback Data | Automated System Process | Recalculation encounters Account with zero Feedback__c records | 1. System queries Feedback__c records for Account 2. System detects zero related Feedback__c records 3. System sets Account.Average_Rating__c to null 4. System sets Account.Feedback_Count__c to 0 5. System updates Account.Rating_Last_Calculated__c with current timestamp | 2a. If Feedback__c records exist but all have null Rating__c: Treat as zero feedback scenario | GIVEN Account has no Feedback__c records WHEN recalculation runs THEN Account.Average_Rating__c is set to null GIVEN Account has no Feedback__c records WHEN recalculation runs THEN Account.Feedback_Count__c equals 0 GIVEN Account previously had ratings but all Feedback__c deleted WHEN recalculation runs THEN Account.Average_Rating__c changes from previous value to null | Account, Feedback__c | Account.Average_Rating__c, Account.Feedback_Count__c, Account.Rating_Last_Calculated__c, Feedback__c.Rating__c
UC-020-01 | BR-020 | View Feedback Related List on Account | Business User | User navigates to Account record page | 1. User opens Account record page 2. System displays Feedback related list component 3. System queries all Feedback__c records where Feedback__c.Account__c = Current Account Id 4. System displays feedback records with key fields in list view 5. User views feedback records without leaving Account page | 3a. If no feedback records exist: Display 'No feedback records to display' message 3b. If user lacks read permission on Feedback__c: Hide related list component | GIVEN Account has 5 feedback records WHEN User opens Account page THEN All 5 feedback records display in related list GIVEN Account has no feedback records WHEN User opens Account page THEN Related list shows empty state message GIVEN User lacks Feedback__c read access WHEN User opens Account page THEN Feedback related list is not visible GIVEN Feedback related list is visible WHEN User views list THEN Feedback__c.Name, Feedback__c.Status__c, Feedback__c.CreatedDate display | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Name, Feedback__c.Status__c, Feedback__c.CreatedDate
UC-020-02 | BR-020 | Navigate to Feedback Record from Account | Business User | User clicks feedback record link in related list | 1. User views Feedback related list on Account page 2. User clicks Feedback__c.Name hyperlink 3. System navigates to Feedback__c record detail page 4. User views full feedback record details | 2a. If user clicks row action menu: Display available actions (Edit, Delete, View) 3a. If record is deleted before navigation: Display error toast 'Record no longer exists' | GIVEN User is on Account page WHEN User clicks feedback record name THEN System opens Feedback__c record page GIVEN User clicks feedback record WHEN Navigation completes THEN Correct Feedback__c record displays GIVEN Feedback record is deleted WHEN User attempts to open THEN Error message displays and user remains on Account page | Account, Feedback__c | Feedback__c.Id, Feedback__c.Name
UC-020-03 | BR-020 | Filter and Sort Feedback Records | Business User | User applies filter or sort on Feedback related list | 1. User views Feedback related list on Account page 2. User clicks column header to sort or applies list view filter 3. System re-queries Feedback__c records with sort/filter criteria 4. System refreshes related list with filtered/sorted results 5. User views updated feedback list | 3a. If filter returns no results: Display 'No items to display' message 2a. If user selects different list view: System applies predefined filter criteria | GIVEN 10 feedback records exist WHEN User sorts by CreatedDate descending THEN Records display newest first GIVEN User applies Status filter WHEN Filter = 'Open' THEN Only feedback records with Status__c = 'Open' display GIVEN User selects 'Recent Feedback' list view WHEN View loads THEN Only records from last 30 days display | Account, Feedback__c | Feedback__c.Status__c, Feedback__c.CreatedDate, Feedback__c.Account__c
UC-020-04 | BR-020 | Create New Feedback from Account Page | Business User | User clicks New button on Feedback related list | 1. User clicks New button in Feedback related list 2. System opens Feedback__c record creation modal 3. System pre-populates Feedback__c.Account__c with current Account Id 4. User enters required fields and clicks Save 5. System creates Feedback__c record and refreshes related list 6. User sees new feedback record in related list | 4a. If required fields missing: Display validation error and prevent save 4b. If user clicks Cancel: Close modal without saving and return to Account page | GIVEN User clicks New on Feedback related list WHEN Modal opens THEN Feedback__c.Account__c is pre-populated with current Account Id GIVEN User enters all required fields WHEN User clicks Save THEN New Feedback__c record is created and related list refreshes GIVEN User omits required field WHEN User clicks Save THEN Validation error displays and record is not created GIVEN New feedback is created WHEN Related list refreshes THEN New record appears at top of list | Account, Feedback__c | Feedback__c.Account__c, Feedback__c.Name, Feedback__c.Status__c, Feedback__c.Description__c

## Marcus - WBS
Phase | Task ID | Task Name | Description | Assigned Agent | Effort (days) | Dependencies | Deliverables | Validation Criteria
Foundation & DevOps Setup | TASK-001 | Configure Git repository and branching strategy | Set up Git repository with trunk-based development strategy, branch protection rules, and commit conventions. | Jordan | 2 |  | Git repository with README, Branch protection rules, Commit convention guide | DONE WHEN: Repository created with main/develop branches and protection rules configured ¦ VERIFIED BY: Clone repository, attempt direct push to main (should fail), check branch rules in GitHub/GitLab settings
Foundation & DevOps Setup | TASK-002 | Set up CI/CD pipeline with automated testing | Configure GitHub Actions or Jenkins pipeline for automated builds, test execution, and code quality checks. | Jordan | 5 | TASK-001 | CI/CD pipeline configuration, Automated test execution, Code quality gates | DONE WHEN: Pipeline runs on every commit, executes tests, and reports coverage ¦ VERIFIED BY: Push test commit, verify pipeline runs successfully, check test results and coverage report in pipeline output
Foundation & DevOps Setup | TASK-003 | Define sandbox strategy and provision environments | Document sandbox purposes (Dev, QA, UAT, Staging), provision sandboxes, and create refresh procedures. | Raj | 3 |  | Sandbox strategy document, Environment inventory, Refresh schedule | DONE WHEN: 4 sandboxes provisioned (Dev, QA, UAT, Staging) with documented purposes ¦ VERIFIED BY: Access each sandbox, verify login works, check sandbox type in Setup > Sandboxes
Foundation & DevOps Setup | TASK-004 | Create core custom objects (Agent, Conversation, Message) | Build Agent__c, Conversation__c, and Message__c objects with all fields, relationships, and validation rules. | Raj | 8 | TASK-003 | 3 custom objects, Field definitions, Validation rules, Page layouts | DONE WHEN: Agent__c, Conversation__c, Message__c objects created with minimum 15 fields each and master-detail relationships ¦ VERIFIED BY: Query SELECT COUNT() FROM Agent__c, Conversation__c, Message__c in Dev sandbox, verify relationships in Schema Builder
Foundation & DevOps Setup | TASK-005 | Create supporting custom objects (Knowledge Article, Agent Capability, User Preference) | Build Knowledge_Article__c, Agent_Capability__c, and User_Preference__c objects with fields and relationships. | Raj | 5 | TASK-004 | 3 custom objects, Lookup relationships, Field-level security | DONE WHEN: Knowledge_Article__c, Agent_Capability__c, User_Preference__c objects created with all specified fields ¦ VERIFIED BY: Run SOQL queries to verify objects exist, check field count matches requirements, test record creation
Foundation & DevOps Setup | TASK-006 | Create custom metadata types for configuration | Build Agent_Configuration__mdt and System_Settings__mdt with fields for managing agent behaviors and system parameters. | Raj | 3 | TASK-004 | 2 custom metadata types, Sample configuration records | DONE WHEN: Agent_Configuration__mdt and System_Settings__mdt created with minimum 5 fields each and 2 sample records ¦ VERIFIED BY: Navigate to Setup > Custom Metadata Types, verify types exist, query records using SOQL
Foundation & DevOps Setup | TASK-007 | Create test data factory and seed data scripts | Build Apex test data factory class and data loader scripts for creating realistic test data. | Diego | 4 | TASK-005 | TestDataFactory.cls, Data loader CSV files, Anonymous Apex scripts | DONE WHEN: TestDataFactory class creates 50+ test records across all objects with realistic data ¦ VERIFIED BY: Execute TestDataFactory methods in anonymous Apex, verify record counts with SOQL queries
Foundation & DevOps Setup | TASK-008 | Review Phase 1 data model architecture | Conduct architecture review of data model design, relationships, and field definitions. | Marcus | 1 | TASK-005, TASK-006 | Architecture review document, Approved data model, Change recommendations | DONE WHEN: Architecture review completed with documented approval or change requests ¦ VERIFIED BY: Review meeting notes exist, all change requests logged with status
Security & Access Control | TASK-009 | Create custom profiles for user roles | Build Agent_Admin, Agent_User, and Knowledge_Manager profiles with appropriate object and field permissions. | Raj | 3 | TASK-005 | 3 custom profiles, Profile permission matrix, Profile assignment guide | DONE WHEN: 3 custom profiles created with documented permissions for all custom objects ¦ VERIFIED BY: Navigate to Setup > Profiles, verify 3 profiles exist, check object permissions match requirements
Security & Access Control | TASK-010 | Create permission sets for feature access | Build Advanced_Analytics, API_Integration_Access, and Agent_Configuration_Manager permission sets. | Raj | 3 | TASK-009 | 5 permission sets, Permission set descriptions, Assignment criteria | DONE WHEN: 5 permission sets created with specific feature permissions documented ¦ VERIFIED BY: Query PermissionSet object, verify count=5, test assignment to test user, verify access granted
Security & Access Control | TASK-011 | Create permission set groups for role-based access | Build permission set groups combining multiple permission sets for common role combinations. | Raj | 2 | TASK-010 | 2 permission set groups, Group membership documentation | DONE WHEN: 2 permission set groups created with minimum 2 permission sets each ¦ VERIFIED BY: Navigate to Setup > Permission Set Groups, verify groups exist, check member permission sets
Security & Access Control | TASK-012 | Configure organization-wide defaults and sharing rules | Set OWD to Private for custom objects and create sharing rules for Agent and Conversation objects. | Raj | 3 | TASK-009 | OWD configuration, 5 sharing rules, Sharing model documentation | DONE WHEN: OWD set to Private for all custom objects and minimum 5 sharing rules created ¦ VERIFIED BY: Check Setup > Sharing Settings, verify OWD settings, test record access with different users
Security & Access Control | TASK-013 | Implement Apex managed sharing classes | Build Apex classes for programmatic sharing to handle complex dynamic access control scenarios. | Diego | 4 | TASK-012 | ConversationSharingService.cls, AgentSharingService.cls, Test classes | DONE WHEN: Apex sharing classes created with methods for grant/revoke access and 85%+ test coverage ¦ VERIFIED BY: Run Apex tests, verify coverage >85%, test sharing grant/revoke in anonymous Apex
Security & Access Control | TASK-014 | Enable Shield Platform Encryption for sensitive fields | Configure Shield Platform Encryption for conversation content, API keys, and PII fields. | Raj | 3 | TASK-005 | Encryption policy, Encrypted field list, Key rotation procedure | DONE WHEN: Shield encryption enabled on minimum 10 sensitive fields across objects ¦ VERIFIED BY: Navigate to Setup > Platform Encryption, verify policy active, check encrypted fields list
Security & Access Control | TASK-015 | Configure Event Monitoring and audit trails | Enable Event Monitoring for security auditing and configure audit trail for sensitive operations. | Raj | 2 | TASK-014 | Event Monitoring configuration, Audit trail settings, Monitoring dashboard | DONE WHEN: Event Monitoring enabled with minimum 5 event types tracked ¦ VERIFIED BY: Check Setup > Event Monitoring, verify event types enabled, query EventLogFile object
Security & Access Control | TASK-016 | Test security model with different user personas | Execute security test plan validating access controls across all profiles and permission sets. | Elena | 4 | TASK-011, TASK-012, TASK-013 | Security test plan, Test execution results, Defect log | DONE WHEN: Security tests executed for 5 user personas with all pass/fail results documented ¦ VERIFIED BY: Review test execution report, verify all test cases have results, check defect count
Core Business Logic & Automation | TASK-017 | Build conversation lifecycle flows | Create record-triggered flows for conversation creation, status updates, and completion handling. | Raj | 5 | TASK-005 | 3 record-triggered flows, Flow documentation, Error handling subflows | DONE WHEN: 3 conversation flows created handling create/update/complete events with error handling ¦ VERIFIED BY: Create test conversation records, verify flows execute, check debug logs for flow execution
Core Business Logic & Automation | TASK-018 | Build message routing and processing flows | Create flows for message routing, sentiment analysis triggering, and response generation orchestration. | Raj | 5 | TASK-017 | 4 message processing flows, Routing logic documentation | DONE WHEN: 4 message flows created handling routing, processing, and response generation ¦ VERIFIED BY: Create test messages, verify routing logic works, check flow interview logs
Core Business Logic & Automation | TASK-019 | Build agent state management flows | Create flows for agent activation, deactivation, status monitoring, and capability updates. | Raj | 4 | TASK-017 | 3 agent management flows, State transition diagram | DONE WHEN: 3 agent flows created managing activation, status changes, and capability updates ¦ VERIFIED BY: Update agent records, verify state transitions work correctly, check flow execution logs
Core Business Logic & Automation | TASK-020 | Build analytics aggregation flows | Create scheduled flows for aggregating conversation metrics, agent performance, and usage statistics. | Raj | 4 | TASK-017 | 3 scheduled flows, Aggregation logic documentation | DONE WHEN: 3 scheduled flows created for daily/weekly/monthly analytics aggregation ¦ VERIFIED BY: Manually run scheduled flows, verify aggregated data created, check scheduled job status
Core Business Logic & Automation | TASK-021 | Implement trigger handler framework | Build reusable trigger handler framework with recursion prevention and bulkification support. | Diego | 3 | TASK-005 | TriggerHandler.cls, TriggerDispatcher.cls, Test classes | DONE WHEN: Trigger framework classes created with recursion prevention and 90%+ test coverage ¦ VERIFIED BY: Run Apex tests for framework classes, verify coverage >90%, test recursion prevention
Core Business Logic & Automation | TASK-022 | Implement Conversation trigger and handler | Build ConversationTrigger and ConversationTriggerHandler for after-insert and after-update logic. | Diego | 4 | TASK-021 | ConversationTrigger, ConversationTriggerHandler.cls, Test classes | DONE WHEN: Conversation trigger created handling after-insert/update with 85%+ test coverage ¦ VERIFIED BY: Run trigger tests, verify coverage >85%, test bulk operations with 200 records
Core Business Logic & Automation | TASK-023 | Implement Message and Agent triggers with handlers | Build MessageTrigger, AgentTrigger and their handler classes for business logic execution. | Diego | 5 | TASK-021 | 2 triggers, 2 handler classes, Test classes | DONE WHEN: Message and Agent triggers created with handlers and 85%+ test coverage each ¦ VERIFIED BY: Run all trigger tests, verify coverage >85% for each, test bulk operations
Core Business Logic & Automation | TASK-024 | Build core service layer classes | Implement AgentService, ConversationService, MessageService classes with business logic methods. | Diego | 8 | TASK-021 | 3 service classes, Service interface definitions, Test classes | DONE WHEN: 3 service classes created with minimum 10 methods each and 85%+ test coverage ¦ VERIFIED BY: Run service class tests, verify coverage >85%, check method count in each class
Core Business Logic & Automation | TASK-025 | Build utility and helper classes | Create utility classes for common operations like date handling, string manipulation, and validation. | Diego | 3 | TASK-024 | 5 utility classes, Test classes | DONE WHEN: 5 utility classes created with 90%+ test coverage ¦ VERIFIED BY: Run utility tests, verify coverage >90%, verify methods are static and reusable
Core Business Logic & Automation | TASK-026 | Test Phase 3 automation and business logic | Execute comprehensive test plan for all flows, triggers, and service classes. | Elena | 6 | TASK-020, TASK-023, TASK-025 | Test plan, Test execution results, Defect log | DONE WHEN: All automation tests executed with minimum 85% pass rate and defects logged ¦ VERIFIED BY: Review test execution report, verify pass rate >85%, check all defects have status
Integration Layer | TASK-027 | Configure Named Credentials for AI services | Set up Named Credentials for OpenAI and Anthropic APIs with authentication and endpoint configuration. | Raj | 2 | TASK-005 | 2 Named Credentials, API key management guide | DONE WHEN: Named Credentials created for OpenAI and Anthropic with test connection successful ¦ VERIFIED BY: Navigate to Setup > Named Credentials, verify 2 credentials exist, test connection button shows success
Integration Layer | TASK-028 | Build OpenAI integration connector class | Implement OpenAIConnector class with methods for chat completion, embeddings, and error handling. | Diego | 5 | TASK-027 | OpenAIConnector.cls, Mock service for testing, Test classes | DONE WHEN: OpenAIConnector class created with 5+ API methods and 85%+ test coverage using mocks ¦ VERIFIED BY: Run connector tests with mocks, verify coverage >85%, test error handling scenarios
Integration Layer | TASK-029 | Build Anthropic integration connector class | Implement AnthropicConnector class with Claude API methods and circuit breaker pattern. | Diego | 5 | TASK-027 | AnthropicConnector.cls, Circuit breaker implementation, Test classes | DONE WHEN: AnthropicConnector class created with circuit breaker and 85%+ test coverage ¦ VERIFIED BY: Run connector tests, verify coverage >85%, test circuit breaker opens after failures
Integration Layer | TASK-030 | Build REST API endpoints for agent interactions | Create @RestResource classes for external systems to interact with agents and conversations. | Diego | 6 | TASK-024 | 3 REST API classes, API documentation, Test classes | DONE WHEN: 3 REST API endpoints created with GET/POST/PUT methods and 85%+ test coverage ¦ VERIFIED BY: Run API tests, verify coverage >85%, test endpoints with Postman or Workbench
Integration Layer | TASK-031 | Create Platform Events for real-time messaging | Build Agent_Status_Change__e, Message_Received__e, Conversation_Update__e Platform Events. | Raj | 3 | TASK-005 | 3 Platform Events, Event payload documentation | DONE WHEN: 3 Platform Events created with minimum 5 fields each ¦ VERIFIED BY: Navigate to Setup > Platform Events, verify 3 events exist, check field definitions
Integration Layer | TASK-032 | Implement Platform Event publishers and subscribers | Build Apex classes to publish and subscribe to Platform Events with error handling. | Diego | 5 | TASK-031 | EventPublisher.cls, EventSubscriber.cls, Test classes | DONE WHEN: Publisher and subscriber classes created with 85%+ test coverage ¦ VERIFIED BY: Run event tests, verify coverage >85%, test publish/subscribe flow in anonymous Apex
Integration Layer | TASK-033 | Build custom logging framework | Create Log__c custom object and LogService class for structured application logging. | Diego | 4 | TASK-005 | Log__c object, LogService.cls, Test classes | DONE WHEN: Log object created with LogService class supporting INFO/WARN/ERROR levels and 85%+ coverage ¦ VERIFIED BY: Run LogService tests, verify coverage >85%, create test logs and query Log__c records
Integration Layer | TASK-034 | Configure monitoring dashboards and alerts | Create dashboards for system health monitoring and configure email alerts for critical errors. | Raj | 3 | TASK-033 | 2 monitoring dashboards, Alert email templates, Alert workflow rules | DONE WHEN: 2 dashboards created showing error rates and system health with alerts configured ¦ VERIFIED BY: View dashboards, verify components display data, trigger test error to verify alert email sent
Integration Layer | TASK-035 | Test integration layer end-to-end | Execute integration test plan covering AI connectors, REST APIs, Platform Events, and logging. | Elena | 5 | TASK-030, TASK-032, TASK-034 | Integration test plan, Test execution results, Performance metrics | DONE WHEN: All integration tests executed with minimum 80% pass rate and performance benchmarks met ¦ VERIFIED BY: Review test results, verify pass rate >80%, check API response times <500ms
User Interface Development | TASK-036 | Build conversationInterface LWC component | Create main conversation interface component with message display, input, and real-time updates. | Zara | 6 | TASK-024, TASK-032 | conversationInterface LWC, Component documentation, Jest tests | DONE WHEN: conversationInterface component created with message display and input with Jest tests passing ¦ VERIFIED BY: Run npm test, verify Jest tests pass, deploy component and test in Lightning App Builder
User Interface Development | TASK-037 | Build agentDashboard LWC component | Create agent dashboard showing agent status, metrics, and configuration options. | Zara | 5 | TASK-024 | agentDashboard LWC, Component documentation, Jest tests | DONE WHEN: agentDashboard component created displaying agent metrics with Jest tests passing ¦ VERIFIED BY: Run npm test, verify tests pass, test component displays data correctly in Lightning page
User Interface Development | TASK-038 | Build messageComposer and knowledgeSearch LWC components | Create message composer with rich text support and knowledge base search component. | Zara | 5 | TASK-024 | 2 LWC components, Component documentation, Jest tests | DONE WHEN: messageComposer and knowledgeSearch components created with Jest tests passing ¦ VERIFIED BY: Run npm test for both components, verify tests pass, test rich text and search functionality
User Interface Development | TASK-039 | Build analyticsCharts LWC component | Create reusable charts component using Chart.js for displaying conversation and agent analytics. | Zara | 4 | TASK-024 | analyticsCharts LWC, Chart.js static resource, Jest tests | DONE WHEN: analyticsCharts component created with 3+ chart types and Jest tests passing ¦ VERIFIED BY: Run npm test, verify tests pass, test component renders bar/line/pie charts correctly
User Interface Development | TASK-040 | Build supporting LWC components (notifications, modals, utilities) | Create reusable utility components for notifications, modals, spinners, and error handling. | Zara | 4 |  | 5+ utility LWC components, Component library documentation | DONE WHEN: Minimum 5 utility components created with Jest tests passing ¦ VERIFIED BY: Run npm test, verify all utility component tests pass, test components in sample page
User Interface Development | TASK-041 | Create Lightning pages for Agent Management and Conversation Console | Build custom Lightning pages using Lightning App Builder with LWC components. | Zara | 3 | TASK-036, TASK-037 | 2 Lightning pages, Page layout documentation | DONE WHEN: Agent Management and Conversation Console Lightning pages created with components configured ¦ VERIFIED BY: Navigate to Lightning pages in Setup, verify pages exist, test pages load correctly with data
User Interface Development | TASK-042 | Create Analytics Dashboard Lightning page | Build analytics dashboard Lightning page with charts, metrics, and filters. | Zara | 3 | TASK-039 | Analytics Dashboard page, Filter configuration | DONE WHEN: Analytics Dashboard page created with minimum 5 chart components and working filters ¦ VERIFIED BY: Open Analytics Dashboard, verify charts display data, test filters update charts
User Interface Development | TASK-043 | Create custom Lightning App and navigation | Build Digital Humans Platform Lightning App with navigation items and utility bar configuration. | Zara | 2 | TASK-041, TASK-042 | Lightning App, Navigation configuration, Utility bar items | DONE WHEN: Digital Humans Platform app created with 5+ navigation items and utility bar configured ¦ VERIFIED BY: Open Lightning App, verify all navigation items work, test utility bar items
User Interface Development | TASK-044 | Upload static resources and configure content assets | Upload JavaScript libraries, CSS files, images, and create content assets for help documentation. | Zara | 2 | TASK-039 | 10+ static resources, Content asset library | DONE WHEN: Minimum 10 static resources uploaded and accessible from components ¦ VERIFIED BY: Navigate to Setup > Static Resources, verify resources exist, test resource loading in components
User Interface Development | TASK-045 | Test UI components and user experience | Execute UI test plan covering all components, pages, and user workflows. | Elena | 5 | TASK-043, TASK-044 | UI test plan, Test execution results, UX feedback report | DONE WHEN: All UI tests executed with minimum 85% pass rate and UX issues documented ¦ VERIFIED BY: Review test results, verify pass rate >85%, check all UX issues logged with severity
Analytics & Reporting | TASK-046 | Create custom report types for complex queries | Build custom report types for Conversations with Messages, Agents with Capabilities, and User Analytics. | Raj | 3 | TASK-005 | 5 custom report types, Report type documentation | DONE WHEN: 5 custom report types created with proper object relationships ¦ VERIFIED BY: Navigate to Setup > Report Types, verify 5 types exist, create test report using each type
Analytics & Reporting | TASK-047 | Create agent performance reports | Build reports showing agent response times, conversation volumes, success rates, and utilization. | Diego | 3 | TASK-046 | 5 agent performance reports, Report folder structure | DONE WHEN: 5 agent reports created showing key performance metrics with filters ¦ VERIFIED BY: Run each report, verify data displays correctly, test filters work, check calculations
Analytics & Reporting | TASK-048 | Create conversation metrics reports | Build reports for conversation duration, message counts, sentiment analysis, and resolution rates. | Diego | 3 | TASK-046 | 5 conversation reports, Report scheduling configuration | DONE WHEN: 5 conversation reports created with trend analysis and scheduled delivery ¦ VERIFIED BY: Run reports, verify metrics calculate correctly, test scheduled delivery works
Analytics & Reporting | TASK-049 | Create user engagement reports | Build reports tracking user activity, adoption metrics, feature usage, and satisfaction scores. | Diego | 2 | TASK-046 | 5 user engagement reports | DONE WHEN: 5 user engagement reports created with adoption metrics ¦ VERIFIED BY: Run reports, verify user activity data displays, test grouping and filtering
Analytics & Reporting | TASK-050 | Create executive summary dashboard | Build executive dashboard with high-level KPIs, trends, and key metrics using dynamic dashboards. | Diego | 3 | TASK-047, TASK-048, TASK-049 | Executive dashboard, Dashboard components documentation | DONE WHEN: Executive dashboard created with minimum 8 components showing KPIs and trends ¦ VERIFIED BY: Open dashboard, verify all components display data, test dynamic filtering works
Analytics & Reporting | TASK-051 | Create operational metrics dashboards | Build operational dashboards for real-time monitoring, system health, and performance tracking. | Diego | 3 | TASK-047, TASK-048 | 2 operational dashboards, Refresh schedule | DONE WHEN: 2 operational dashboards created with real-time metrics and auto-refresh configured ¦ VERIFIED BY: Open dashboards, verify real-time data updates, test auto-refresh works
Analytics & Reporting | TASK-052 | Configure report folders and sharing | Organize reports into folders with appropriate sharing settings for different user roles. | Raj | 1 | TASK-047, TASK-048, TASK-049 | Report folder structure, Folder sharing configuration | DONE WHEN: Report folders created with role-based sharing configured ¦ VERIFIED BY: Check report folders exist, test access with different user profiles, verify sharing works
Analytics & Reporting | TASK-053 | Test reports and dashboards accuracy | Validate all reports and dashboards show accurate data and calculations are correct. | Elena | 3 | TASK-050, TASK-051 | Report validation test plan, Test results, Data accuracy report | DONE WHEN: All reports and dashboards tested with 100% accuracy validation ¦ VERIFIED BY: Review test results, verify all calculations checked, confirm data matches source records
Operations & Maintenance | TASK-054 | Build conversation archival batch job | Create batch Apex class to archive old conversations and related records based on retention policy. | Diego | 4 | TASK-024 | ConversationArchivalBatch.cls, Schedulable class, Test classes | DONE WHEN: Batch class created with proper batch sizing and 85%+ test coverage ¦ VERIFIED BY: Run batch tests, verify coverage >85%, execute batch with test data, verify archival works
Operations & Maintenance | TASK-055 | Build analytics aggregation batch job | Create batch job to aggregate daily/weekly/monthly analytics and update summary records. | Diego | 4 | TASK-024 | AnalyticsAggregationBatch.cls, Schedulable class, Test classes | DONE WHEN: Batch class created with aggregation logic and 85%+ test coverage ¦ VERIFIED BY: Run batch tests, verify coverage >85%, execute batch, verify aggregated data created
Operations & Maintenance | TASK-056 | Build data cleanup batch job | Create batch job for cleaning up orphaned records, expired sessions, and temporary data. | Diego | 3 | TASK-024 | DataCleanupBatch.cls, Schedulable class, Test classes | DONE WHEN: Batch class created with cleanup logic and 85%+ test coverage ¦ VERIFIED BY: Run batch tests, verify coverage >85%, execute batch, verify cleanup works correctly
Operations & Maintenance | TASK-057 | Schedule batch jobs and configure monitoring | Schedule all batch jobs with appropriate timing and configure monitoring for job failures. | Raj | 2 | TASK-054, TASK-055, TASK-056 | Job schedule configuration, Monitoring alerts, Job execution log | DONE WHEN: All 3 batch jobs scheduled with monitoring alerts configured ¦ VERIFIED BY: Check scheduled jobs in Setup, verify schedules correct, trigger test failure to verify alert
Operations & Maintenance | TASK-058 | Create technical architecture documentation | Document system architecture, data model, integration patterns, and design decisions. | Diego | 4 | TASK-030, TASK-043 | Architecture document, Data model diagrams, Integration diagrams | DONE WHEN: Architecture documentation complete with minimum 10 diagrams and ADRs ¦ VERIFIED BY: Review documentation, verify all major components documented, check diagrams render correctly
Operations & Maintenance | TASK-059 | Create API documentation and developer guide | Document all REST APIs, Platform Events, and provide developer guide with code examples. | Diego | 3 | TASK-030, TASK-032 | API documentation, Developer guide, Code examples | DONE WHEN: API documentation complete with examples for all endpoints and events ¦ VERIFIED BY: Review documentation, verify all APIs documented, test code examples work
Operations & Maintenance | TASK-060 | Create deployment and operations runbooks | Document deployment procedures, rollback plans, monitoring procedures, and troubleshooting guides. | Diego | 3 | TASK-002 | Deployment runbook, Operations runbook, Troubleshooting guide | DONE WHEN: Runbooks created covering deployment, monitoring, and common issues ¦ VERIFIED BY: Review runbooks, verify procedures are step-by-step, test deployment procedure works
Operations & Maintenance | TASK-061 | Create user training materials | Develop user guides, video tutorials, and quick reference cards for end users. | Lucas | 5 | TASK-043 | User guide, Video tutorials, Quick reference cards | DONE WHEN: Training materials created covering all major features with minimum 5 video tutorials ¦ VERIFIED BY: Review all materials, verify completeness, test videos play correctly
Operations & Maintenance | TASK-062 | Conduct administrator training sessions | Deliver training sessions for system administrators covering configuration, monitoring, and maintenance. | Lucas | 3 | TASK-061 | Training session materials, Training attendance records, Training feedback | DONE WHEN: Minimum 2 admin training sessions delivered with 80%+ satisfaction rating ¦ VERIFIED BY: Review attendance records, check feedback forms, verify satisfaction >80%
Testing & Quality Assurance | TASK-063 | Execute integration testing across all components | Test end-to-end workflows across UI, business logic, integrations, and data layers. | Elena | 6 | TASK-043, TASK-035 | Integration test plan, Test execution results, Defect log | DONE WHEN: All integration test scenarios executed with minimum 85% pass rate ¦ VERIFIED BY: Review test results, verify pass rate >85%, check all defects logged with priority
Testing & Quality Assurance | TASK-064 | Execute performance and load testing | Test system performance under load including concurrent users, bulk operations, and API response times. | Elena | 5 | TASK-063 | Performance test plan, Load test results, Performance benchmarks | DONE WHEN: Load testing completed with 100 concurrent users and all benchmarks met ¦ VERIFIED BY: Review load test results, verify page load <2s, API response <500ms, no governor limit errors
Testing & Quality Assurance | TASK-065 | Execute security testing and vulnerability assessment | Perform security testing including penetration testing, OWASP top 10 checks, and data access validation. | Elena | 4 | TASK-063 | Security test plan, Vulnerability assessment report, Remediation plan | DONE WHEN: Security testing completed with no critical vulnerabilities and remediation plan for medium issues ¦ VERIFIED BY: Review security report, verify no critical issues, check remediation plan exists for all findings
Testing & Quality Assurance | TASK-066 | Execute user acceptance testing with pilot users | Conduct UAT with pilot user group covering all major user workflows and scenarios. | Elena | 5 | TASK-063 | UAT test plan, UAT execution results, User feedback report | DONE WHEN: UAT completed with minimum 10 pilot users and 80%+ acceptance rate ¦ VERIFIED BY: Review UAT results, verify 10+ users participated, check acceptance rate >80%
Testing & Quality Assurance | TASK-067 | Execute regression testing for all fixes | Run regression test suite to verify defect fixes and ensure no new issues introduced. | Elena | 4 | TASK-063, TASK-064, TASK-065 | Regression test results, Final defect status report | DONE WHEN: Regression testing completed with 95%+ pass rate and all critical defects resolved ¦ VERIFIED BY: Review regression results, verify pass rate >95%, check no open critical defects
Testing & Quality Assurance | TASK-068 | Verify code coverage and quality metrics | Validate overall code coverage meets 85% threshold and code quality standards are met. | Elena | 2 | TASK-067 | Code coverage report, Code quality report, Quality gate status | DONE WHEN: Code coverage verified at 85%+ and all quality gates passed ¦ VERIFIED BY: Run apex:test:run with coverage, verify coverage >85%, check SonarQube or PMD results
Testing & Quality Assurance | TASK-069 | Create test summary and sign-off documentation | Compile comprehensive test summary report with all test results and obtain stakeholder sign-off. | Elena | 2 | TASK-068 | Test summary report, Sign-off document, Known issues log | DONE WHEN: Test summary report completed with stakeholder sign-off obtained ¦ VERIFIED BY: Review test summary, verify all test phases covered, check sign-off signatures present
Deployment & Go-Live | TASK-070 | Prepare production deployment package | Create deployment package with all metadata, data, and configuration for production deployment. | Jordan | 3 | TASK-069 | Deployment package, Deployment checklist, Rollback plan | DONE WHEN: Deployment package created with all components and validated in staging ¦ VERIFIED BY: Deploy to staging sandbox, verify all components deploy successfully, test rollback procedure
Deployment & Go-Live | TASK-071 | Execute production deployment | Deploy all components to production environment following deployment runbook. | Jordan | 2 | TASK-070 | Deployment log, Deployment verification results | DONE WHEN: All components deployed to production with zero deployment errors ¦ VERIFIED BY: Review deployment log, verify all components deployed, run deployment verification tests
Deployment & Go-Live | TASK-072 | Execute production smoke testing | Run smoke test suite in production to verify all critical functionality works. | Elena | 2 | TASK-071 | Smoke test results, Production validation report | DONE WHEN: Smoke tests executed in production with 100% pass rate ¦ VERIFIED BY: Review smoke test results, verify all critical paths tested, check 100% pass rate
Deployment & Go-Live | TASK-073 | Configure production monitoring and alerts | Set up production monitoring dashboards, error alerts, and performance tracking. | Raj | 2 | TASK-071 | Production monitoring dashboards, Alert configuration, On-call procedures | DONE WHEN: Production monitoring active with alerts configured and tested ¦ VERIFIED BY: View monitoring dashboards, trigger test alert, verify alert received by on-call team
Deployment & Go-Live | TASK-074 | Load production seed data | Load initial configuration data, sample agents, and knowledge base content to production. | Aisha | 2 | TASK-071 | Data load log, Data validation report | DONE WHEN: Production seed data loaded with validation confirming data integrity ¦ VERIFIED BY: Run data validation queries, verify record counts match expectations, test data access
Deployment & Go-Live | TASK-075 | Conduct end-user training for go-live | Deliver final training sessions for end users before go-live. | Lucas | 3 | TASK-072 | Training session recordings, Training materials, User feedback | DONE WHEN: Minimum 3 end-user training sessions delivered with 80%+ satisfaction ¦ VERIFIED BY: Review attendance records, check feedback forms, verify satisfaction >80%
Deployment & Go-Live | TASK-076 | Execute go-live and hypercare support | Execute go-live procedures and provide intensive support during first week of production use. | Marcus | 5 | TASK-072, TASK-073, TASK-074, TASK-075 | Go-live checklist, Hypercare log, Issue resolution log | DONE WHEN: Go-live completed with 5 days of hypercare support and all critical issues resolved ¦ VERIFIED BY: Review hypercare log, verify all issues tracked, check critical issues resolved within SLA
Deployment & Go-Live | TASK-077 | Conduct post-implementation review | Review project delivery, lessons learned, and create recommendations for future phases. | Marcus | 2 | TASK-076 | Post-implementation review document, Lessons learned, Future recommendations | DONE WHEN: Post-implementation review completed with documented lessons learned and recommendations ¦ VERIFIED BY: Review PIR document, verify all stakeholders provided input, check recommendations documented

## Marcus - Gap Analysis
Gap ID | Category | Current State | Target State | Gap Description | Priority | Effort | Dependencies
GAP-001-01 | DATA_MODEL | No custom objects exist. Standard Salesforce objects only. | Custom objects for Agent, Conversation, Message, Knowledge_Article__c, Agent_Capability__c, and User_Preference__c with full field definitions and relationships. | Complete data model implementation required including 6 custom objects, approximately 50+ custom fields, lookup/master-detail relationships, validation rules, and record types. | Critical | 15 | Diego
GAP-001-02 | DATA_MODEL | No custom metadata types configured. | Custom metadata types for Agent_Configuration__mdt and System_Settings__mdt to manage agent behaviors and system parameters. | Need to create custom metadata types for configuration management to avoid hard-coding values and enable admin-friendly configuration. | High | 3 | Diego | GAP-001-01
GAP-001-03 | SECURITY | Only standard profiles exist. No custom profiles, permission sets, or permission set groups. | Custom profiles for Agent_Admin, Agent_User, Knowledge_Manager. Permission sets for Advanced_Analytics, API_Integration_Access, Agent_Configuration_Manager. Permission set groups for role-based access. | Complete security model implementation required with 3 custom profiles, 5+ permission sets, 2+ permission set groups, and field-level security configuration. | Critical | 8 | Zara | GAP-001-01
GAP-001-04 | SECURITY | Default sharing model with no custom sharing rules. | Organization-wide defaults set to Private for custom objects. Sharing rules for Agent and Conversation objects. Apex managed sharing for dynamic access control. | Need to implement comprehensive sharing model including OWD configuration, sharing rules, and programmatic sharing for multi-tenant data isolation. | High | 5 | Zara | GAP-001-01, GAP-001-03
GAP-001-05 | AUTOMATION | No flows, triggers, or automation configured. | 15+ flows including record-triggered flows for Agent lifecycle, screen flows for user interactions, autolaunched flows for batch processing. Platform Events for real-time updates. | Complete automation layer required including conversation orchestration, message routing, agent state management, and analytics aggregation flows. | Critical | 20 | Zara | GAP-001-01, GAP-001-03
GAP-001-06 | AUTOMATION | No Apex triggers exist. | Apex triggers for complex business logic including ConversationTrigger, MessageTrigger, AgentTrigger with trigger handler framework. | Need to implement trigger framework with handlers for after-insert, after-update operations on core objects. Include bulkification and recursion prevention. | High | 8 | Raj | GAP-001-01, GAP-001-05
GAP-001-07 | INTEGRATION | No integrations configured. No connected apps, named credentials, or external services. | REST API endpoints for agent interactions, Named Credentials for OpenAI/Anthropic, Connected App for mobile access, Platform Events for real-time messaging, Streaming API for live updates. | Complete integration layer required including external AI service integration, REST API development, real-time event streaming, and webhook support. | Critical | 18 | Raj | GAP-001-01, GAP-001-03, GAP-001-06
GAP-001-08 | INTEGRATION | No Platform Events defined. | Platform Events for Agent_Status_Change__e, Message_Received__e, Conversation_Update__e to enable real-time communication. | Need to create and configure Platform Events for event-driven architecture supporting real-time updates across the platform. | High | 5 | Raj | GAP-001-01
GAP-001-09 | UI | No custom Lightning pages, LWC components, or Aura components. | 20+ LWC components including conversationInterface, agentDashboard, messageComposer, knowledgeSearch, analyticsCharts. Custom Lightning pages for Agent Management, Conversation Console, Analytics Dashboard. | Complete UI layer implementation required with custom Lightning Web Components, Lightning pages, custom tabs, and Lightning App Builder configurations. | Critical | 25 | Zara | GAP-001-01, GAP-001-05, GAP-001-07
GAP-001-10 | UI | No custom applications or tabs configured. | Custom Lightning App 'Digital Humans Platform' with navigation items for Agents, Conversations, Knowledge Base, Analytics, Settings. | Need to create custom Lightning application with branded navigation, utility bar items, and role-based app visibility. | Medium | 2 | Zara | GAP-001-01, GAP-001-09
GAP-001-11 | OTHER | No Apex classes deployed. Code coverage N/A. | 50+ Apex classes including service layer (AgentService, ConversationService), integration layer (OpenAIConnector, AnthropicConnector), utility classes, and comprehensive test classes achieving 85%+ coverage. | Complete Apex codebase required including service classes, integration handlers, batch jobs, schedulable classes, queueable jobs, and test coverage. | Critical | 30 | Raj | GAP-001-01, GAP-001-03, GAP-001-07
GAP-001-12 | OTHER | No batch or scheduled jobs configured. | Batch jobs for conversation archival, analytics aggregation, data cleanup. Scheduled jobs for nightly processing and maintenance tasks. | Need to implement batch Apex classes and schedulable classes for background processing, data maintenance, and periodic analytics updates. | Medium | 8 | Raj | GAP-001-01, GAP-001-11
GAP-001-13 | OTHER | No reports or dashboards configured. | 15+ reports covering agent performance, conversation metrics, user engagement. 5+ dashboards for real-time monitoring, executive summary, operational metrics. | Complete reporting and analytics layer including custom report types, reports, dashboards, and Einstein Analytics integration. | Medium | 10 | Diego | GAP-001-01, GAP-001-05
GAP-001-14 | OTHER | No static resources or content assets. | Static resources for JavaScript libraries, CSS frameworks, images, icons. Content assets for knowledge base articles and help documentation. | Need to upload and configure static resources for UI components, third-party libraries, and content management. | Low | 3 | Zara | GAP-001-09
GAP-001-15 | OTHER | No DevOps pipeline or source control integration. | Git repository with branch strategy, CI/CD pipeline using GitHub Actions or Jenkins, automated testing, code quality checks, and deployment automation. | Need to establish complete DevOps infrastructure including source control, automated builds, testing, and deployment processes. | High | 7 | Raj
GAP-001-16 | OTHER | No monitoring or logging infrastructure. | Custom logging framework using custom objects, Event Monitoring enabled, Shield Platform Encryption for sensitive data, monitoring dashboards for system health. | Need to implement comprehensive logging, monitoring, and observability infrastructure for production support and troubleshooting. | High | 6 | Raj | GAP-001-01, GAP-001-11
GAP-001-17 | SECURITY | No encryption or data protection measures beyond standard Salesforce security. | Shield Platform Encryption for sensitive fields, Event Monitoring for audit trails, Transaction Security policies for anomaly detection. | Need to implement advanced security features including field encryption, comprehensive audit logging, and security monitoring. | High | 5 | Zara | GAP-001-01, GAP-001-03
GAP-001-18 | OTHER | No documentation or architecture decision records. | Comprehensive technical documentation including architecture diagrams, API documentation, deployment guides, runbooks, ADRs for key decisions. | Need to create complete documentation suite covering architecture, development standards, operational procedures, and decision rationale. | Medium | 8 | Diego | GAP-001-01, GAP-001-05, GAP-001-07, GAP-001-09, GAP-001-11
GAP-001-19 | DATA_MODEL | No sample or seed data for testing and development. | Comprehensive test data sets including sample agents, conversations, messages, knowledge articles for development and UAT environments. | Need to create realistic test data sets that cover various scenarios, edge cases, and volume testing requirements. | Medium | 4 | Diego | GAP-001-01
GAP-001-20 | OTHER | No sandbox strategy or environment management plan. | Defined sandbox strategy with Dev, QA, UAT, and Staging environments. Refresh schedules, data seeding procedures, and environment-specific configurations. | Need to establish sandbox governance including environment purposes, refresh cadence, data management, and promotion paths. | High | 3 | Diego | GAP-001-15

## Marcus - Solution
Section | Component | Details
Standard Object | Account | Fields:
Custom Object | Customer_Feedback__c | Fields: Rating__c (Picklist), Comments__c (Long Text Area(32768)), Feedback_Date__c (Date), Account__c (Lookup(Account)), Sentiment_Score__c (Number(3,2)), Submitted_By__c (Lookup(Contact))
Profile | Sales User Profile
Profile | Support Agent Profile
Profile | Business Analyst Profile
Permission Set | Customer_Feedback_Admin
Permission Set | Customer_Feedback_Reporter
Flow |  | Screen Flow - Provides guided interface for customers/users to submit feedback with validation
Flow |  | Record-Triggered Flow - Auto-populate Feedback_Date__c if blank (UC-004-01)
Trigger |  | On Customer_Feedback__c - ['after insert', 'after update', 'after delete', 'after undelete']
LWC Component |  | Allow users to submit new feedback from Account page (UC-002-01, UC-003-01)
LWC Component |  | Display chronological history of feedback on Account (UC-002-04)
LWC Component |  | Visual display of account's average rating with star graphics
Risk | RISK-001 [Low/High] | Trigger may hit SOQL query limits if processing feedbacks for >100 unique accounts in single transaction - Mitigation: Implement trigger handler with bulkification. Use single SOQL query with WHERE IN clause. Add error handling and logging. Monitor trigger execution in production.
Risk | RISK-002 [Medium/Medium] | Historical data import may have invalid ratings or missing account references - Mitigation: Create data validation rules before import. Use CSV template with picklist values. Perform dry-run in sandbox. Implement validation rule: Rating__c IN ('1','2','3','4','5').
Risk | RISK-003 [Low/Medium] | LWC component may load slowly on accounts with 500+ feedback records - Mitigation: Implement pagination in feedbackTimeline component. Limit initial load to 20 records. Use lazy loading for additional records. Add loading spinner.
Risk | RISK-004 [Medium/High] | Users may not adopt new feedback system if too complex - Mitigation: Simplify UI to 2 required fields (Rating, Account auto-populated). Provide training materials. Create Quick Action for mobile users. Gather feedback in UAT.
Risk | RISK-005 [Low/Medium] | Einstein Sentiment API may have availability or cost issues - Mitigation: Make sentiment analysis optional/nice-to-have. Implement retry logic with exponential backoff. Monitor API usage and costs. Consider alternative: simple keyword-based sentiment.
Risk | RISK-006 [Medium/High] | Sensitive customer comments may be visible to unauthorized users - Mitigation: Implement Private OWD with sharing rules. Use Permission Sets for admin access. Enable Field Audit Trail. Review sharing model with security team before deployment.
Risk | RISK-007 [Low/High] | Trigger may interfere with existing Account automation - Mitigation: Review all existing Account triggers and workflows. Implement trigger framework to control execution order. Test in full-copy sandbox with production data. Create rollback plan.

## Elena - QA
QA Specifications (raw)

## Jordan - DevOps
DevOps Specifications

## Aisha - Data
Data Specifications

## Lucas - Training
Training Specifications